# Pre-mortem Guide

How to surface the risks people are quietly worried about, by imagining the work has already failed.

Facilitator Run-Sheet · Run a Project · Inspired by Gary Klein's Pre-mortem

“It's six months from now and this has failed. What happened?”

Asking “what could go wrong?” gets polite, cautious answers. A pre-mortem, developed by psychologist Gary Klein, asks the group to imagine the project has already failed and explain why. This prospective hindsight makes it safe to voice worries, and it surfaces far more risks. The group then votes on the most likely causes and agrees how to prevent them, or at least detect them early.

| Duration | Group | Use when | Output |
| --- | --- | --- | --- |
| 45–60 min | Team, PO, sponsor, key stakeholders | Before a project, release or big decision | Top risks with prevention & signals |

# Before the session

- Print the board at A3, or load the SVG as a digital background

- Make sure everyone understands the plan being tested: share it beforehand

- Pink stickies, markers and dot stickers (3 per person)

- Invite people with different views, including sceptics

- Bring the RAID Log so top risks can be added straight away

# Agenda & run-sheet

| Time | Section | Facilitator notes |
| --- | --- | --- |
| 0–5 | 1 · The Scenario | Fill in a date in the future. Read the scenario aloud: “It's that date and this has failed badly.” |
| 5–15 | 2 · Why It Failed (silent) | Everyone writes reasons alone, one per sticky, in the past tense. No discussion yet. |
| 15–30 | Share & cluster | Go round the room, one sticky at a time, until all are up. Cluster similar reasons. |
| 30–35 | Dot vote | Three dots each, on the reasons most likely to actually happen. |
| 35–40 | 3 · Top Risks | Write the top 5–8 in the table with votes, likelihood and impact. |
| 40–55 | 4 · Prevent or Detect | For each top risk, agree a prevention, an early warning sign and an owner. |
| 55–60 | 5 · Next Steps | Tick off the follow-ups and set a review date. |

# Making each section strong

Quality checks for each part of the board.

## 1 · The Scenario

- A specific future date

- Failure is described concretely

## 2 · Why It Failed

- Written in the past tense

- Silent writing first

- Wide range of causes

## 3 · Top Risks

- Chosen by vote

- Likelihood and impact noted

## 4 · Prevent or Detect

- A real prevention or a clear warning sign

- Every risk has an owner

## 5 · Next Steps

- Risks reach the RAID Log

- A review date is set

# Facilitation tips

Past tense matters. “We lost our key engineer” feels more real than “we might lose someone”, and gets better answers.

Silent first. Writing alone stops the most senior or loudest person shaping everyone's thinking.

Welcome the uncomfortable. The most valuable reasons are often about decisions, leadership or politics. Thank people for them.

Not just doom. Close by focusing on what you'll do. The goal is a better plan, not a gloomy team.

Prevent or detect. If a risk can't be prevented, agree the early warning sign that would tell you it's happening.

Repeat it. Run a short pre-mortem again before each big milestone.

Common pitfalls: discussing reasons before everyone has written; the sponsor dismissing reasons in the room; only listing technical risks; no owners for actions; not feeding risks into the RAID Log or the plan.

# After the session

Straight away: Add the top risks to the RAID Log and the prevention actions to the backlog.

This week: Put the early warning signs where the team will notice them.

Each iteration: Check the warning signs at the review or retro.

Before milestones: Run a quick pre-mortem again on the next phase.

# How it fits the toolkit

The project tools work together: run a Project Kickoff first, then build the Stakeholder Map, keep the RAID Log up to date, and refresh the Release Forecast after every iteration. Inside the project, teams use the lifecycle tools (Team Charter, Prioritisation, Sprint Planning and Review) and the break-down tools.

Boards: https://eparker71.github.io/agile-ways-of-working/pre-mortem-board.html  ·  Online guide: https://eparker71.github.io/agile-ways-of-working/facilitator-guide-pre-mortem.html

© 2026 Eric Parker · CC BY 4.0 · eparker71.github.io/agile-ways-of-working · Adapt it freely; please keep the credit and say what you changed.