# Buffering & Swarming Guide

How to size a capacity buffer from real data, agree swarm triggers, and make swarming a team habit.

Facilitator Run-Sheet · Manage Flow · Capacity Buffer · Swarm Triggers

“What would we stop starting so we could finish this?”

Two habits keep work flowing when reality interrupts the plan. Buffering means deliberately leaving part of the team's capacity unplanned, sized from how much unplanned work actually arrives, so surprises don't wreck the plan. Swarming means that when an item is blocked, ageing or critical, people stop starting new work and gather on it until it's done. The board helps the team size the buffer, agree its rules, set clear triggers, agree how a swarm works, and learn from each one.

| Duration | Group | Use when | Output |
| --- | --- | --- | --- |
| 60–75 min to set up 10 min each retro | The whole team, PO included | Plans keep breaking, or work stalls | A buffer, rules & swarm triggers |

# Before the session

- Print the board at A3, or load the SVG as a digital background

- Pull data for the last five iterations: planned capacity and unplanned work (items, points or hours)

- If you have them, bring cycle time percentiles from the Ageing WIP board

- Bring the Skills Matrix if the team has one: it shows who can help in a swarm

- Agree with the PO in advance that a buffer is a planning tool, not idle time

# Agenda & run-sheet

| Time | Section | Facilitator notes |
| --- | --- | --- |
| 0–15 | 1 · Unplanned Work History | Fill in the table from the data. Work out the average % unplanned. Discuss what kinds of work it was. |
| 15–25 | 2 · Size the Buffer | Start with the average % unplanned as the buffer. Agree what it protects. |
| 25–35 | 3 · Buffer Rules | Agree what counts as unplanned, who decides to use the buffer, and what happens if it runs out or isn't used. |
| 35–50 | 4 · Swarm Triggers | Tick the triggers that fit and fill in the thresholds. Use your 85% SLE for the age trigger. |
| 50–65 | 5 · How We Swarm | Walk through the five steps. Agree who calls a swarm, and how people join. Add notes to each step. |
| 65–75 | Close | Agree to try it for two iterations, logging every swarm, then review at the retro. |

# Making each section strong

Quality checks for each part of the board.

## 1 · Unplanned Work History

- Based on data, not memory

- Types of unplanned work noted

## 2 · Size the Buffer

- Starts from the real average

- Clear what it's for

## 3 · Buffer Rules

- Unused buffer goes to improvement or the next item

- Running out triggers a conversation

## 4 · Swarm Triggers

- Specific thresholds

- Linked to the SLE

- Few enough to remember

## 5 · How We Swarm

- Anyone can call a swarm

- Just enough people join

- Finishing beats starting

## 6 · Swarm Log

- Every swarm recorded

- Learning captured

## 7 · Iteration Check

- Buffer adjusted from use

- Did swarms help?

# Facilitation tips

Buffers aren't slack. A buffer is planned capacity for work you know will come. Unused, it goes to improvement or the next item.

Size from data. If 20% of the team's time goes on unplanned work, planning for 100% guarantees a missed plan.

Swarm on the oldest. When in doubt, swarm on the item that has been open longest, not the newest.

Stop starting first. The first step of a swarm is to not pick up anything new. That alone frees people up.

Not everyone, every time. A swarm needs enough people to finish the item, not the whole team crowded round.

Ask why it needed a swarm. Frequent swarms point to a cause: big items, missing skills, or blockers. Use Blocker Clustering.

Common pitfalls: a buffer that managers fill with extra features; triggers so vague nobody acts; swarming on everything; the same expert always rescuing; never logging swarms, so nothing is learned; swarming without stopping new work.

# After the session

Straight away: Put the triggers and swarm steps on the team board where everyone can see them.

Every day: At the daily sync, check: has anything hit a trigger? Call the swarm then.

Every retro: Run the iteration check: buffer used, swarms, did they help? Adjust the buffer.

Over time: If the same skill always needs the same person, update the Skills Matrix and learning plan.

# How it fits the toolkit

The flow pack works as a set. Kanban Board Design makes the workflow visible and limits WIP. Ageing WIP & SLE shows which items are at risk and sets the swarm triggers used in Buffering & Swarming. Blocker Clustering finds why work gets stuck, and the Skills Matrix shows who can swarm. Bring the results to retrospectives and the Team Health Check.

Boards: https://eparker71.github.io/agile-ways-of-working/buffering-swarming-board.html  ·  Online guide: https://eparker71.github.io/agile-ways-of-working/facilitator-guide-buffering-swarming.html

© 2026 Eric Parker · CC BY 4.0 · eparker71.github.io/agile-ways-of-working · Adapt it freely; please keep the credit and say what you changed.