# Impediments Board Guide

How to make impediments visible, give each one an owner, escalate on time, and show the value of removing them.

Facilitator Run-Sheet · Manage Flow · Team Impediments · Escalation Ladder

“What's slowing us down that we've stopped noticing?”

An impediment is anything that limits how well the team works and that the team can't easily fix alone: a slow approval, a missing tool, an unclear decision owner, a flaky environment. Unlike a blocker on a single item, impediments often affect everything. The board makes each one visible with what it costs, gives it an owner, and uses an escalation ladder with time limits so nothing sits unresolved for weeks. The resolved log shows stakeholders the value of removing impediments.

| Duration | Group | Use when | Output |
| --- | --- | --- | --- |
| 30 min to set up 5 min each day | The team, with the SM or coach | Always on, next to the team board | Owned impediments & a resolved log |

# Before the session

- Print the board at A3 and put it next to the team board, or keep a digital copy

- Pink and green stickies, and markers

- Agree with management who sits on rungs 3 and 4 of the ladder, and that they'll respond in time

- Bring any impediments from recent retros or the Blocker Clustering board

# Agenda & run-sheet

| When | Step | Facilitator notes |
| --- | --- | --- |
| Set-up · 0–10 | 2 · Escalation Ladder | Agree who is on each rung and how many days an impediment stays at a level before moving up. |
| Set-up · 10–25 | 1 · Seed the board | Brainstorm current impediments. One pink sticky each: what, what it costs us, owner, date raised. |
| Set-up · 25–30 | Prioritise | Order by cost. Agree a next step for the top ones and move them to Being worked. |
| Daily | Review | At the daily sync, check the board. Anything past its time limit moves up the ladder. |
| When resolved | 3 · Resolved Log | Add a green sticky saying what fixed it. Record it in the log with the days open and the lesson. |
| Each retro | Look back | Review what was resolved, what's stuck, and whether the ladder's time limits are working. |

# Making each part work

Quality checks for each part of the board.

## 1 · Impediments

- Each sticky shows its cost

- Each has an owner and a date

- Few in Being worked at once

## 2 · Escalation Ladder

- Named people at every rung

- Time limits are short

- Leaders agreed to respond

## 3 · Resolved Log

- What it cost and what fixed it

- Shared with stakeholders

- Lessons feed improvement

# Facilitation tips

Show the cost. “Waiting 3 days for approvals each sprint” gets action. “Approvals are slow” doesn't.

Owner, not escalator. The owner drives the impediment to resolution, even after it's escalated.

Time-box each rung. Without a time limit, impediments sit at the team level for months.

Limit work in progress. Work on a few impediments at a time and finish them, just like backlog items.

Celebrate removals. Share the resolved log at reviews. It builds support for removing the next one.

Look for patterns. If the same kind keeps appearing, it's a system issue. Raise it at the retro or with leaders.

Common pitfalls: a board full of complaints with no owners; no time limits; escalating without the data on cost; leaders who don't respond; the SM fixing everything alone; never recording what was resolved.

# After the session

Straight away: Put the board where the team and visitors can see it.

Every day: Check it at the daily sync and move anything past its time limit.

Each review: Share the resolved log and any escalations that need stakeholder help.

Quarterly: Look at the log for patterns and bring them to the Team Health Check or leaders.

# How it fits the toolkit

The flow pack works as a set. Kanban Board Design makes the workflow visible and limits WIP. Ageing WIP & SLE shows which items are at risk and sets the swarm triggers used in Buffering & Swarming. Blocker Clustering finds why work gets stuck, and the Skills Matrix shows who can swarm. Bring the results to retrospectives and the Team Health Check.

Boards: https://eparker71.github.io/agile-ways-of-working/impediments-board.html  ·  Online guide: https://eparker71.github.io/agile-ways-of-working/facilitator-guide-impediments.html

© 2026 Eric Parker · CC BY 4.0 · eparker71.github.io/agile-ways-of-working · Adapt it freely; please keep the credit and say what you changed.