# Backlog Refinement Guide

How to run a regular refinement session that gets the next items ordered, understood, split, sized and ready.

Facilitator Run-Sheet · Run Events · Backlog Refinement

“Which items do we need ready for the next iteration?”

Refinement is the ongoing work of getting the next few backlog items ready: ordered by value, understood by the team, split small enough to finish in a few days, explored through examples, and roughly sized. Scrum describes it as an ongoing activity rather than a formal event. Many teams hold a regular session, often taking around 10% of their capacity. The board walks each item through six steps and points to the toolkit tool for each one, so the session stays focused and finishes with ready items.

| Duration | Group | Use when | Output |
| --- | --- | --- | --- |
| 45–90 min, weekly | PO, developers, testers, experts | Every week, or before planning | Ready items for the next 1–2 iterations |

# Before the session

- Print the board at A3 or 11×17, or load the SVG as a digital background

- The PO brings the top items in order, with any context or data

- Have the Story Splitting poster and Example Mapping board to hand

- Agree the team's Definition of Ready, if you have one

- Invite experts only for the items that need them

# Agenda & run-sheet

| Minutes | Step | Facilitator notes |
| --- | --- | --- |
| 0–5 | 1 · Session goal | Agree which items to refine and the iteration they need to be ready for. |
| 5–15 | Order | Confirm the order with the PO. Drop or defer anything no longer valuable. |
| 15–60 | Understand · Split · Examples | For each item: who it's for and why, split it if it's too big, then map rules and examples. |
| 60–75 | Size | Size the items quickly, or check they're small enough to count. |
| 75–85 | Ready? | Check each item against the Definition of Ready. Record open questions with owners. |
| 85–90 | Close | Read back what's ready and what isn't, and when the next session is. |

# Making each step strong

Quality checks for each step of the flow.

## Order

- Most valuable first

- Drop what's no longer needed

## Understand

- Who it's for, and why

- What done looks like

## Split

- Finishes in a few days

- Vertical slices

## Examples

- Rules and examples

- Questions have owners

## Size

- Relative and quick

- Or just count small items

## Ready?

- Checked against the DoR

- A guide, not a gate

# Facilitation tips

Just in time. Refine one or two iterations ahead. Refining further out wastes effort when plans change.

Whole team. Developers and testers find hidden work and risks the PO can't see alone.

Timebox each item. If an item takes more than 15–20 minutes, it probably needs splitting or a spike.

Questions are progress. An open question found now is cheaper than one found mid-iteration.

Don't design it all. Agree enough to start. The team will work out details while building.

Little and often. A short weekly session beats one long, tiring one before planning.

Common pitfalls: refining too far ahead; the PO presenting while the team listens; designing solutions in detail; no splitting; endless debate on one item; treating the Definition of Ready as a gate.

# After the session

Straight away: Update the backlog: splits, examples, sizes and open questions.

Before planning: Question owners find the answers.

At planning: Ready items go in first.

At the retro: Ask whether items arrived in planning ready enough.

# How it fits the toolkit

The event tools follow a team's rhythm: Sprint Planning or replenishment, the Daily Sync, Backlog Refinement, Sprint Review and a retrospective from the Retro Kit. Teams working in continuous flow use the Kanban Cadences. The Events & Cadences poster shows them all, including multi-team and leadership events.

# Recreate it in your whiteboard

Paste this into your whiteboard's AI assistant (for example Miro AI or Atlassian Rovo) or a general assistant, to get an editable, native version of the board. Results vary by tool, so expect to tidy it up. For an exact copy, import the SVG as a locked background instead.

Create an editable whiteboard for “Backlog Refinement”, a workshop board.

Purpose: Get the next few items ordered, understood, split, sized and ready, in one focused session.

Layout: a wide landscape board (about 16:11). Make one frame per section below, placed as described. In each frame, add the section name as a heading, then its content as short text labels or empty fields to fill in. Leave space in each frame for sticky notes. Use the header colour given. Keep the wording as written and don't add extra content.

Header fields to fill in: Team, Date

Sections:

1. Session Goal: top full width, about 100% wide and 15% tall; header colour slate grey.

Subtitle: Refine just enough, just in time

Content: Items to refine: · Ready for (iteration or date): · Who's here:

2. Refinement Flow: middle full width, about 100% wide and 50% tall; header colour blue.

Subtitle: For each item, in order · stop when it's ready

Content: 1. 2 · 3. 4 · 5. 6 · Order · Understand · Split · Examples · Size · Ready? · Is this still the most · Who is it for, and why? · Can we finish it in a few · Rules, examples and · Roughly how big, compared · Check it against our · valuable next item? · What does done look like? · days? If not, slice it. · open questions. · with things we've done? · Definition of Ready. · → Prioritisation Board · → Backlog Item Anatomy · → Story Splitting · → Example Mapping · → Estimation · → panel 4, below · Our note: (×6)

3. Items Refined: bottom left, about 65% wide and 30% tall; header colour emerald green.

Content: Item: · Split into: · Examples agreed: · Size: · Ready? · Open questions & owner:

4. Definition of Ready: bottom right, about 35% wide and 30% tall; header colour amber.

Subtitle: A guide, not a gate

Content: Who it's for and why is clear · Small enough to finish in a few days · Examples or acceptance criteria agreed · Dependencies known and handled · No open question that would stop work · Next refinement:

Footer questions: “Which items do we need ready for the next iteration?” “What don't we know yet that would stop us starting?”

Original board for reference: https://eparker71.github.io/better-delivery-toolkit/boards/backlog-refinement-board.html

Boards: https://eparker71.github.io/better-delivery-toolkit/boards/backlog-refinement-board.html  ·  Online guide: https://eparker71.github.io/better-delivery-toolkit/guides/facilitator-guide-backlog-refinement.html

© 2026 Eric Parker · CC BY 4.0 · eparker71.github.io/better-delivery-toolkit · Adapt it freely; please keep the credit and say what you changed.