# Design Sprint Guide

How to run a five-day design sprint: map the problem, sketch, decide, build a realistic prototype and test it with customers.

Facilitator Run-Sheet · Decide What to Build · Design Sprint (Jake Knapp, GV)

“What question, if answered on Friday, would make this week worth it?”

A design sprint answers a big product question in five days instead of months. Developed by Jake Knapp at Google Ventures and described in Sprint (2016), it takes a small team through Map (Monday), Sketch (Tuesday), Decide (Wednesday), Prototype (Thursday) and Test (Friday) with five real customers. A named Decider makes the hard calls, so the week ends with evidence instead of opinions. Many teams now run a compressed four-day version; the board works for both.

| Duration | Group | Use when | Output |
| --- | --- | --- | --- |
| Four or five full days | Up to seven, including a Decider and a facilitator | A big, risky question with no clear answer | A tested prototype and a decision |

# Before the session

- Print the board at A3 or 11×17 and keep it on the wall all week, or use the SVG on a digital whiteboard

- Agree the challenge and the Decider at least a week before

- Clear everyone's diaries for the whole week; devices away during sessions

- Start recruiting five target customers for Friday before the sprint begins

- Book a room with lots of wall space, and line up experts to interview on Monday

# Agenda & run-sheet

| Day | Section | Facilitator notes |
| --- | --- | --- |
| Before | 1 · Challenge · 2 · Team | Write the challenge, name the Decider and the roles, and book the customers. |
| Monday | 3 · Map | Set the long-term goal and sprint questions, map the journey, interview experts, pick a target. |
| Tuesday | 4 · Sketch | Lightning demos for inspiration, then everyone sketches a solution alone. |
| Wednesday | 5 · Decide | Silent gallery, heat-map dots, straw poll; the Decider chooses. Storyboard the prototype. |
| Thursday | 6 · Prototype | Build only the façade customers will see. Trial run and finish the interview script. |
| Friday | 7 · Test · 8 · Results · 9 · Next | Five interviews while the team watches. Mark the grid, find patterns, decide. |

# What each day produces

Each day's output feeds the next.

## Map

- Goal and questions

- A target on the map

## Sketch

- Individual solutions

- Five customers booked

## Decide

- A winning idea

- A storyboard

## Prototype

- A realistic façade

- An interview script

## Test

- Five interviews

- Patterns and a decision

# Facilitation tips

Together alone. People work silently and individually, then the group critiques; it beats brainstorming.

Respect the Decider. Input is welcome, but the Decider decides. That's what keeps the week moving.

Façade, not product. Build just enough to feel real for an interview. Slides or a clickable mock-up are often enough.

Five is enough. Patterns usually show up after five interviews; more adds little in a week.

Watch behaviour. What customers do with the prototype matters more than what they say about it.

Timebox hard. The schedule is tight on purpose. Use a visible timer for every activity.

Common pitfalls: no real Decider; people dropping in and out; a challenge that's too small or already decided; recruiting customers too late; building a real product on Thursday; arguing about results instead of looking for patterns.

# After the session

Monday after: Share the results, the patterns and the decision with stakeholders.

If it worked: Turn the prototype into a backlog with the Epic Breakdown Canvas and Story Map.

If it didn't: A failed test in a week is a win; decide whether to iterate or stop.

Next time: Run a short retro on the sprint format itself.

# How it fits the toolkit

A design sprint fits in discovery. Use the Opportunity Solution Tree or Product Bet Canvas to choose the challenge, the Persona & Journey Map for Monday's map, and the Epic Breakdown Canvas and User Story Map to turn a winning prototype into work.

# Recreate it in your whiteboard

Paste this into your whiteboard's AI assistant (for example Miro AI or Atlassian Rovo) or a general assistant, to get an editable, native version of the board. Results vary by tool, so expect to tidy it up. For an exact copy, import the SVG as a locked background instead.

Create an editable whiteboard for “Design Sprint”, a workshop board.

Purpose: Answer a big question in five days: map the problem, sketch ideas, decide, build a realistic prototype and test it with customers.

Layout: a wide landscape board (about 16:11). Make one frame per section below, placed as described. In each frame, add the section name as a heading, then its content as short text labels or empty fields to fill in. Leave space in each frame for sticky notes. Use the header colour given. Keep the wording as written and don't add extra content.

Header fields to fill in: Sprint, Dates, Decider

Sections:

1. Challenge & Goal: top left, about 50% wide and 25% tall; header colour slate grey.

Subtitle: Monday morning

Content: The challenge: · Long-term goal (in two years…): · Sprint questions (what could stop us?):

2. The Sprint Team: top right, about 50% wide and 25% tall; header colour sky blue.

Subtitle: Seven or fewer

Content: Decider: · Facilitator: · Customer expert: · Tech expert: · Design: · Business / money:

3. Map: middle left, about 20% wide and 55% tall.

Subtitle: Monday

Content: Agree the long-term goal · Map the customer journey · Ask the experts; note “How might we…?” · Pick a target on the map · What we produced: · Stickies, sketches, photos · Our target:

4. Sketch: middle left, about 20% wide and 55% tall; header colour purple.

Subtitle: Tuesday

Content: Lightning demos of existing ideas · Sketch solutions alone, in four steps · Recruit five customers for Friday · What we produced: · Stickies, sketches, photos · Sketches made:

5. Decide: middle centre, about 20% wide and 55% tall; header colour orange.

Subtitle: Wednesday

Content: Silent gallery and heat-map dots · Straw poll, then the Decider chooses · Storyboard the prototype · What we produced: · Stickies, sketches, photos · Winning idea:

6. Prototype: middle right, about 20% wide and 55% tall.

Subtitle: Thursday

Content: Build a realistic façade, not the product · Split roles: makers, writer, stitcher · Trial run; write the interview script · What we produced: · Stickies, sketches, photos · Prototype is a:

7. Test: middle right, about 20% wide and 55% tall; header colour dark green.

Subtitle: Friday

Content: Five one-to-one customer interviews · The team watches and takes notes · Look for patterns across interviews · What we produced: · Stickies, sketches, photos · Patterns we saw:

8. Friday's Results: bottom left, about 65% wide and 20% tall; header colour dark green.

Subtitle: ✓ worked · ✗ didn't · ? unclear

Content: Sprint question or target: · Customer 1: · Customer 2: · Customer 3: · Customer 4: · Customer 5:

9. What Next?: bottom right, about 35% wide and 20% tall; header colour red.

Subtitle: The decider calls it

Content: Build it · Iterate and test again · Change direction · Stop here · First step and owner:

Footer questions: “What question, if answered on Friday, would make this week worth it?” “What did customers do, not just say?”

Original board for reference: https://eparker71.github.io/better-delivery-toolkit/boards/design-sprint-board.html

Boards: https://eparker71.github.io/better-delivery-toolkit/boards/design-sprint-board.html  ·  Online guide: https://eparker71.github.io/better-delivery-toolkit/guides/facilitator-guide-design-sprint.html

© 2026 Eric Parker · CC BY 4.0 · eparker71.github.io/better-delivery-toolkit · Adapt it freely; please keep the credit and say what you changed.