# Estimation Guide

How to size work quickly and fairly with planning poker, T-shirt sizing or affinity estimation, or skip it.

Facilitator Run-Sheet · Iterate · Planning Poker · T-Shirt Sizing · Affinity Estimation

“Is this bigger or smaller than the last thing we finished?”

Estimates help teams plan and spot items that are too big, but they cost time and are often misused. The board offers three ways to estimate relatively, comparing items with each other rather than guessing hours. Planning poker (described by James Grenning, popularised by Mike Cohn) suits a handful of items. T-shirt sizing roughly sorts many items. Affinity estimation sizes a whole backlog in an hour. It also suggests the alternative many teams find works as well: split items small and count them.

| Duration | Group | Use when | Output |
| --- | --- | --- | --- |
| 15–60 min | The people who will do the work | Planning, refinement, or release forecasting | Relative sizes or a count |

# Before the session

- Print the board at A3 or 11×17, or load the SVG as a digital background

- Bring the items to estimate, ideally refined with Example Mapping first

- Agree 3–5 reference items everyone remembers, for the Reference Items table

- Planning poker cards, or a phone app, if you use poker

# Agenda & run-sheet

| Use | Technique | How to run it |
| --- | --- | --- |
| A few items | 1 · Planning Poker | Read the item, everyone picks a card privately, reveal together. The highest and lowest explain, then re-vote. Two rounds at most. |
| Many items | 2 · T-Shirt Sizing | Agree what a reference “M” is, then place each item in XS to XL. Discuss only items people disagree on. |
| A whole backlog | 3 · Affinity Estimation | Silently place items left to right by size. Anyone can move anything. Discuss items that keep moving, then draw boundaries. |
| Any | 4 · Reference Items | Keep shared examples for each size, and compare new items against them. |
| Consider | 5 · Don't Estimate | If items are split to finish within your SLE, count them and forecast from throughput instead. |

# Choosing a technique

Pick the lightest technique that gives you what you need.

## Planning Poker

- A few items in detail

- Surfaces different assumptions

## T-Shirt Sizing

- Rough sizes for roadmaps

- Quick for many items

## Affinity Estimation

- A whole backlog

- Mostly silent, very fast

## Reference Items

- Keep sizes consistent

- Update occasionally

## Don't Estimate

- Right-size and count

- Forecast from throughput

# Facilitation tips

The conversation is the value. When estimates differ, the discussion reveals hidden work or risk.

Relative beats absolute. People compare sizes far better than they guess hours.

Don't average. If votes differ widely, talk and re-vote. Averaging hides the disagreement.

Split the big ones. Anything at 13 or above is usually too big. Split it before estimating again.

Estimates aren't promises. Use them to forecast, never to judge people or compare teams. An early guess with little to go on (a WAG) should say so, as a wide range.

Try counting. Many teams find counting small items forecasts as accurately as points, with less effort.

Common pitfalls: estimating in hours; managers estimating for the team; averaging votes; treating points as a performance measure; comparing velocity across teams; spending longer estimating than the work would take.

# After the session

Straight away: Record sizes in your backlog tool and note any items to split.

Planning: Use sizes or counts with recent throughput to plan capacity.

Each retro: Compare forecasts with what happened, and adjust.

Every few months: Try a few iterations of counting items, and compare the forecast accuracy.

# How it fits the toolkit

The lifecycle tools follow the work from start to finish: a Team Charter when a team forms, a Product Vision Board to agree why the product exists, the Prioritisation Board to decide what comes first, then Sprint Planning and Sprint Review each iteration, with a retrospective from the Retro Kit to close the loop. The break-down tools (Epic Canvas, Story Map, Story Splitting, Example Mapping) sit between vision and planning.

# Recreate it in your whiteboard

Paste this into your whiteboard's AI assistant (for example Miro AI or Atlassian Rovo) or a general assistant, to get an editable, native version of the board. Results vary by tool, so expect to tidy it up. For an exact copy, import the SVG as a locked background instead.

Create an editable whiteboard for “Estimation”, a workshop board.

Purpose: Size work together quickly with planning poker, T-shirt sizes or affinity estimation, or decide not to estimate.

Layout: a wide landscape board (about 16:11). Make one frame per section below, placed as described. In each frame, add the section name as a heading, then its content as short text labels or empty fields to fill in. Leave space in each frame for sticky notes. Use the header colour given. Keep the wording as written and don't add extra content.

Header fields to fill in: Team, Date

Sections:

1. Planning Poker: top left, about 50% wide and 35% tall; header colour purple.

Subtitle: For a handful of items

Content: 1. 2 · 3. 5 · 8. 13 · 20. ? · ☕ · 1. Read the item · 2. Pick a card privately · 3. Reveal together · 4. Highest and lowest explain · 5. Re-vote, two rounds at most · Item: · Round 1: · Round 2: · Estimate:

2. T-Shirt Sizing: top right, about 50% wide and 35% tall; header colour blue.

Subtitle: For many items, roughly

Content: XS · S · M · L · XL · Reference item that is an “M”:

3. Affinity Estimation: middle left, about 65% wide and 45% tall; header colour orange.

Subtitle: For a whole backlog in an hour

Content: Silently place items left to right, smallest to largest. Anyone can move any item. · Then discuss items that keep moving, and draw size boundaries. · Smaller: · Larger: · 1. 2 · 3. 5 · 8. 13

4. Reference Items: middle right, about 35% wide and 45% tall; header colour emerald green.

Subtitle: Shared examples keep sizes consistent

Content: Size: · Item everyone remembers: · Why this size:

5. Or Don't Estimate: bottom left, about 65% wide and 15% tall; header colour slate grey.

Subtitle: Counting items often forecasts just as well

Content: If items are split small enough to finish within your SLE, count them instead of sizing them. · Forecast from throughput with the Release Forecast board. · We'll try counting items instead of estimating for · iterations, then compare

6. Ground Rules: bottom right, about 35% wide and 15% tall; header colour red.

Content: Estimates belong to the people doing the work · An estimate is a forecast, not a promise · Never compare points between teams

Footer questions: “Is this bigger or smaller than the last thing we finished?” “Do we need a number, or do we just need to know it's small?”

Original board for reference: https://eparker71.github.io/better-delivery-toolkit/boards/estimation-board.html

Boards: https://eparker71.github.io/better-delivery-toolkit/boards/estimation-board.html  ·  Online guide: https://eparker71.github.io/better-delivery-toolkit/guides/facilitator-guide-estimation.html

© 2026 Eric Parker · CC BY 4.0 · eparker71.github.io/better-delivery-toolkit · Adapt it freely; please keep the credit and say what you changed.