# Pre-mortem Guide

How to surface the risks people are quietly worried about, by imagining the work has already failed.

Facilitator Run-Sheet · Run a Project · Inspired by Gary Klein's Pre-mortem

“It's six months from now and this has failed. What happened?”

Asking “what could go wrong?” gets polite, cautious answers. A pre-mortem, developed by psychologist Gary Klein, asks the group to imagine the project has already failed and explain why. This prospective hindsight makes it safe to voice worries, and it surfaces far more risks. The group then votes on the most likely causes and agrees how to prevent them, or at least detect them early.

| Duration | Group | Use when | Output |
| --- | --- | --- | --- |
| 45–60 min | Team, PO, sponsor, key stakeholders | Before a project, release or big decision | Top risks with prevention & signals |

# Before the session

- Print the board at A3 or 11×17, or load the SVG as a digital background

- Make sure everyone understands the plan being tested: share it beforehand

- Pink stickies, markers and dot stickers (3 per person)

- Invite people with different views, including sceptics

- Bring the RAID Log so top risks can be added straight away

# Agenda & run-sheet

| Time | Section | Facilitator notes |
| --- | --- | --- |
| 0–5 | 1 · The Scenario | Fill in a date in the future. Read the scenario aloud: “It's that date and this has failed badly.” |
| 5–15 | 2 · Why It Failed (silent) | Everyone writes reasons alone, one per sticky, in the past tense. No discussion yet. |
| 15–30 | Share & cluster | Go round the room, one sticky at a time, until all are up. Cluster similar reasons. |
| 30–35 | Dot vote | Three dots each, on the reasons most likely to actually happen. |
| 35–40 | 3 · Top Risks | Write the top 5–8 in the table with votes, likelihood and impact. |
| 40–55 | 4 · Prevent or Detect | For each top risk, agree a prevention, an early warning sign and an owner. |
| 55–60 | 5 · Next Steps | Tick off the follow-ups and set a review date. |

# Making each section strong

Quality checks for each part of the board.

## 1 · The Scenario

- A specific future date

- Failure is described concretely

## 2 · Why It Failed

- Written in the past tense

- Silent writing first

- Wide range of causes

## 3 · Top Risks

- Chosen by vote

- Likelihood and impact noted

## 4 · Prevent or Detect

- A real prevention or a clear warning sign

- Every risk has an owner

## 5 · Next Steps

- Risks reach the RAID Log

- A review date is set

# Facilitation tips

Past tense matters. “We lost our key engineer” feels more real than “we might lose someone”, and gets better answers.

Silent first. Writing alone stops the most senior or loudest person shaping everyone's thinking.

Welcome the uncomfortable. The most valuable reasons are often about decisions, leadership or politics. Thank people for them.

Not just doom. Close by focusing on what you'll do. The goal is a better plan, not a gloomy team.

Prevent or detect. If a risk can't be prevented, agree the early warning sign that would tell you it's happening.

Repeat it. Run a short pre-mortem again before each big milestone.

Common pitfalls: discussing reasons before everyone has written; the sponsor dismissing reasons in the room; only listing technical risks; no owners for actions; not feeding risks into the RAID Log or the plan.

# After the session

Straight away: Add the top risks to the RAID Log and the prevention actions to the backlog.

This week: Put the early warning signs where the team will notice them.

Each iteration: Check the warning signs at the review or retro.

Before milestones: Run a quick pre-mortem again on the next phase.

# How it fits the toolkit

The project tools work together: run a Project Kickoff first, then build the Stakeholder Map, keep the RAID Log up to date, and refresh the Release Forecast after every iteration. Inside the project, teams use the lifecycle tools (Team Charter, Prioritisation, Sprint Planning and Review) and the break-down tools.

# Recreate it in your whiteboard

Paste this into your whiteboard's AI assistant (for example Miro AI or Atlassian Rovo) or a general assistant, to get an editable, native version of the board. Results vary by tool, so expect to tidy it up. For an exact copy, import the SVG as a locked background instead.

Create an editable whiteboard for “Pre-mortem”, a workshop board.

Purpose: Imagine the work has already failed, explain why, then act now to prevent the most likely causes.

Layout: a wide landscape board (about 16:11). Make one frame per section below, placed as described. In each frame, add the section name as a heading, then its content as short text labels or empty fields to fill in. Leave space in each frame for sticky notes. Use the header colour given. Keep the wording as written and don't add extra content.

Key: Pink Sticky = Why it failed · Dot = Vote (3 per person)

Sections:

1. The Scenario: top full width, about 100% wide and 20% tall; header colour purple.

Subtitle: Read it aloud · speak as if it has already happened

Content: It's · and this has failed badly. What went wrong? · Project, plan or release: · Failure looks like:

2. Why It Failed: middle left, about 65% wide and 45% tall; header colour red.

Subtitle: Silent writing first · one reason per sticky

Content: Everyone writes alone for 5 minutes, in the past tense: “We lost our key supplier” · Think wide: people, tech, customers, money, dependencies, decisions · Pink stickies, clustered by theme

3. Top Risks: middle right, about 35% wide and 45% tall; header colour orange.

Subtitle: After dot voting

Content: # · Reason: · Likely: · Impact: · Votes:

4. Prevent or Detect: bottom left, about 65% wide and 35% tall; header colour dark green.

Subtitle: For each top risk

Content: Top risk: · We'll prevent it by…: · Early warning sign: · Owner:

5. Next Steps: bottom right, about 35% wide and 35% tall; header colour emerald green.

Content: Top risks added to the RAID Log · Prevention actions added to the backlog · Warning signs visible on the team board · Plan or scope changed where needed · Re-run before the next big milestone · Review these risks on:

Footer questions: “It's six months from now and this has failed. What happened?” “Which of these are we quietly hoping won't happen?”

Original board for reference: https://eparker71.github.io/better-delivery-toolkit/boards/pre-mortem-board.html

Boards: https://eparker71.github.io/better-delivery-toolkit/boards/pre-mortem-board.html  ·  Online guide: https://eparker71.github.io/better-delivery-toolkit/guides/facilitator-guide-pre-mortem.html

© 2026 Eric Parker · CC BY 4.0 · eparker71.github.io/better-delivery-toolkit · Adapt it freely; please keep the credit and say what you changed.