# RACI & Decision Log Guide

How to agree who is responsible and accountable for each piece of work, and keep a clear record of decisions.

Facilitator Run-Sheet · Run a Project · RACI · Decision Log

“Who is accountable for this, just one person?”

Confusion about roles slows projects down: work falls between people, or several people think they decide. A RACI matrix lists the work, deliverables or decisions, and for each role marks who is Responsible (does it), Accountable (owns the outcome, exactly one person), Consulted (gives input) and Informed (kept up to date). The decision log records key decisions, the options considered and why, so the same debates don't restart every month. Use it alongside the Delegation Board, which covers how much a team decides.

| Duration | Group | Use when | Output |
| --- | --- | --- | --- |
| 45–60 min | PM, sponsor, key role holders | A project starts, or roles feel unclear | An agreed matrix & a decision log |

# Before the session

- Print the board at A3 or 11×17, or load the SVG as a digital background

- List the main work items, deliverables and decisions in advance

- List the roles (not names, where possible): sponsor, product owner, team lead, architect and so on

- Invite the people in those roles, so they agree to what's assigned

# Agenda & run-sheet

| Time | Section | Facilitator notes |
| --- | --- | --- |
| 0–10 | Set up | Write the roles across the top and the work items down the side. |
| 10–35 | 1 · Fill in | For each row, agree the A first, then the Rs, then the Cs and Is. |
| 35–45 | 2 · Check | Run the five checks. Fix rows with no A, two As, or too many Cs. |
| 45–55 | 3 · Decision log | Record any decisions already made, with the options and the reasons. |
| 55–60 | Close | Agree where the matrix and log live, and who keeps them current. |

# Making it work

Quality checks for the matrix and the log.

## Responsible

- Does the work

- Can be several people

## Accountable

- Owns the outcome

- Exactly one person

## Consulted

- Gives input before

- Keep the list short

## Informed

- Told after

- No input expected

## Decision Log

- Options and reasons

- A revisit trigger

# Facilitation tips

One A, always. Shared accountability means no accountability. Pick one person.

Watch the Cs. Every consulted person adds delay. Make some of them Informed instead.

Roles, not names. Use roles so the matrix survives people changing.

Agree, don't assign. People named on the matrix should agree to it, or it won't hold.

Log the why. Recording why a decision was made is more useful than the decision itself.

Set revisit triggers. Say what would make you revisit a decision, such as new data or a budget change.

Common pitfalls: two As on a row; everyone Consulted on everything; a matrix nobody agreed to; using RACI to avoid conversations; a decision log with no reasons; never updating either.

# After the session

Straight away: Share the matrix with everyone named and store it with the project.

Each decision: Add it to the log within a day, with the options and the reasons.

When people change: Review the matrix with new role holders.

At project close: Use the decision log in the lessons-learned session.

# How it fits the toolkit

The project tools work together: run a Project Kickoff first, then build the Stakeholder Map, keep the RAID Log up to date, and refresh the Release Forecast after every iteration. Inside the project, teams use the lifecycle tools (Team Charter, Prioritisation, Sprint Planning and Review) and the break-down tools.

# Recreate it in your whiteboard

Paste this into your whiteboard's AI assistant (for example Miro AI or Atlassian Rovo) or a general assistant, to get an editable, native version of the board. Results vary by tool, so expect to tidy it up. For an exact copy, import the SVG as a locked background instead.

Create an editable whiteboard for “RACI & Decision Log”, a workshop board.

Purpose: Agree who does, owns, advises on and hears about each piece of work, and keep a record of key decisions.

Layout: a wide landscape board (about 16:11). Make one frame per section below, placed as described. In each frame, add the section name as a heading, then its content as short text labels or empty fields to fill in. Leave space in each frame for sticky notes. Use the header colour given. Keep the wording as written and don't add extra content.

Header fields to fill in: Project, Date

Sections:

1. RACI Matrix: top full width, about 100% wide and 50% tall; header colour blue.

Subtitle: R responsible · A accountable (one only) · C consulted · I informed

Content: Role 1: · Role 2: · Role 3: · Role 4: · Role 5: · Role 6: · Role 7: · Role 8: · Work, deliverable or decision:

2. Check the Matrix: middle full width, about 100% wide and 10% tall; header colour amber.

Content: Exactly one A in every row · Every row has at least one R · Few Cs: each one slows a decision · No one is R for everything · The people named have agreed

3. Decision Log: bottom full width, about 100% wide and 35% tall; header colour purple.

Subtitle: What we decided, why, and when to revisit

Content: # · Date: · Decision: · Options considered: · Why: · Decided by: · Revisit when:

Footer questions: “Who is accountable for this, just one person?” “Why did we decide that, and what would make us revisit it?”

Original board for reference: https://eparker71.github.io/better-delivery-toolkit/boards/raci-decision-log-board.html

Boards: https://eparker71.github.io/better-delivery-toolkit/boards/raci-decision-log-board.html  ·  Online guide: https://eparker71.github.io/better-delivery-toolkit/guides/facilitator-guide-raci-decision-log.html

© 2026 Eric Parker · CC BY 4.0 · eparker71.github.io/better-delivery-toolkit · Adapt it freely; please keep the credit and say what you changed.