# Release Forecast Guide

How to forecast a release date as a range, using a burn-up chart and the team's real throughput.

Facilitator Run-Sheet · Run a Project · Burn-up · Throughput Forecasting · Ranges, Not Dates

“When will it be done? Here's the range, and here's what it depends on.”

A single delivery date is a guess presented as a fact. The forecast board uses what the team has actually finished each iteration to give a range: slow, likely and fast. The burn-up chart shows done work rising toward a total-scope line, so scope growth is visible rather than hidden. Counting items usually works as well as story points if items are similar in size. For more precision, a Monte Carlo simulation can use the same data.

| Duration | Group | Use when | Output |
| --- | --- | --- | --- |
| 30–45 min to set up | PO, delivery lead, team rep | A release or project with a target date | A dated range & its assumptions |

# Before the session

- Print the board at A3 or 11×17, or load the SVG as a digital background

- Collect done items per iteration for at least the last 3–5 iterations (more is better)

- Count the items remaining in the release, and estimate how much scope usually grows

- Agree whether you're counting items or points, and stick to it

- Bring the iteration calendar so you can turn iterations into dates

# Agenda & run-sheet

| Time | Step | Facilitator notes |
| --- | --- | --- |
| 0–10 | 2 · Throughput Data | Fill in done, added and total scope for each past iteration. Work out the average, slowest 3 and fastest 3. |
| 10–20 | 1 · Burn-up Chart | Set the scale, plot the done line and the total scope line, and draw the fast and slow forecast lines forward. |
| 20–30 | 3 · The Forecast | Divide remaining items by each rate to get iterations left, then convert to dates. Share all three. |
| 30–40 | 4 · What Would Change It | List what would move the forecast: scope growth, people changes, dependencies. Agree when to update it. |
| Every iteration | Update | Add the latest iteration, re-plot, and re-forecast. Share the new range and what changed. |

# Reading the board

What each part tells you.

## 1 · Burn-up Chart

- Gap between lines = work left

- Rising scope line = growth

- Lines not meeting = not converging

## 2 · Throughput Data

- Use real data, not targets

- Note unusual iterations

## 3 · The Forecast

- Always share the range

- Likely isn't a promise

## 4 · What Would Change It

- Assumptions are explicit

- An update date is set

# Facilitation tips

Ranges build trust. A range that holds is more useful than a date that slips. Explain why there's a range.

Show the scope line. Burn-down charts hide scope growth. Burn-ups make it visible, so trade-offs become a conversation.

Count items. If items are roughly similar in size, counting them is simpler than points and just as accurate.

Include growth. Scope almost always grows. Add the team's usual growth rate to the remaining work.

Re-forecast often. Update every iteration. The range narrows as you learn.

Don't push the rate. If the forecast is too late, change scope or the date. Asking the team to “go faster” just adds risk.

Common pitfalls: sharing only the likely date; using a target velocity instead of real data; hiding scope growth; forecasting from one iteration; treating the forecast as a commitment; never updating it.

# After the session

Straight away: Share the range and assumptions with the sponsor and key stakeholders.

Every iteration: Update the data, re-plot the chart and re-forecast.

At the Sprint Review: Show the burn-up chart. Discuss scope trade-offs if the range moves.

If the range slips: Act early: cut scope, remove a dependency, or agree a new date range.

# How it fits the toolkit

The project tools work together: run a Project Kickoff first, then build the Stakeholder Map, keep the RAID Log up to date, and refresh the Release Forecast after every iteration. Inside the project, teams use the lifecycle tools (Team Charter, Prioritisation, Sprint Planning and Review) and the break-down tools.

# Recreate it in your whiteboard

Paste this into your whiteboard's AI assistant (for example Miro AI or Atlassian Rovo) or a general assistant, to get an editable, native version of the board. Results vary by tool, so expect to tidy it up. For an exact copy, import the SVG as a locked background instead.

Create an editable whiteboard for “Release Forecast & Burn-up”, a workshop board.

Purpose: Answer “when will it be done?” with a range, based on how fast the team actually finishes work.

Layout: a wide landscape board (about 16:11). Make one frame per section below, placed as described. In each frame, add the section name as a heading, then its content as short text labels or empty fields to fill in. Leave space in each frame for sticky notes. Use the header colour given. Keep the wording as written and don't add extra content.

Header fields to fill in: Release / Scope, Forecast Date

Sections:

1. Burn-up Chart: top left, about 65% wide and 65% tall; header colour blue.

Subtitle: Plot after every iteration

Content: 1. 2 · 3. 4 · 5. 6 · 7. 8 · 9. 10 · 11. 12 · Iteration →: · Total scope · Done · Forecast range (fast / slow)

2. Throughput Data: top right, about 35% wide and 65% tall; header colour emerald green.

Subtitle: Items finished per iteration

Content: Iteration: · Done: · Added: · Total scope: · Average per iteration: · Slowest 3, average: · Fastest 3, average:

3. The Forecast: bottom left, about 50% wide and 35% tall; header colour amber.

Subtitle: Remaining / rate = iterations left

Content: Remaining items (incl. expected growth): · Scenario: · Rate / iteration: · Iterations left: · Date: · Slow · Likely · Fast

4. What Would Change It: bottom right, about 50% wide and 35% tall; header colour red.

Subtitle: Update the forecast when these move

Content: Scope growth · team changes · dependencies · item size changing · Share the range and the assumptions, not just the likely date · Next forecast update:

Footer questions: “When will it be done? Here's the range, and here's what it depends on.” “What would have to be true for the fast forecast to happen?”

Original board for reference: https://eparker71.github.io/better-delivery-toolkit/boards/release-forecast-board.html

Boards: https://eparker71.github.io/better-delivery-toolkit/boards/release-forecast-board.html  ·  Online guide: https://eparker71.github.io/better-delivery-toolkit/guides/facilitator-guide-release-forecast.html

© 2026 Eric Parker · CC BY 4.0 · eparker71.github.io/better-delivery-toolkit · Adapt it freely; please keep the credit and say what you changed.