# Outcome Status Report Guide

How to write a one-page update built on outcomes, a forecast range, risks and the decisions you need.

Facilitator Run-Sheet · Run a Project · Outcomes Over Output · Decisions, Not Just Status

“What decision do we need, and from whom?”

Traditional status reports turn amber when it's already too late, and rarely ask for anything. This one-page report leads with a headline, a confidence rating and its trend, then shows progress on outcomes, the forecast range and what moved it, what was delivered and learned, the top risks, and the decisions needed. It's built from boards the team already keeps, so it takes minutes, not hours, to write.

| Duration | Group | Use when | Output |
| --- | --- | --- | --- |
| 20–30 min to prepare | PM or program lead, with the PO | Every 2–4 weeks, or for steering | A one-page update & clear asks |

# Before the session

- Print the board at A3 or 11×17, or use a digital copy for each report

- Bring the latest Release Forecast, RAID Log and value or OKR measures

- Check what was released or demonstrated since the last report

- Know who the readers are and what decisions they own (see the Stakeholder Map)

# Agenda & run-sheet

| Step | Section | Notes |
| --- | --- | --- |
| 1 | 2 · Outcomes | Update each outcome measure: start, now, target and trend. |
| 2 | 3 · Forecast | Copy the range from the Release Forecast. Say if it moved, and why. |
| 3 | 4 · Delivered & Learned | List working, in-use deliveries and anything that changed your thinking. |
| 4 | 5 · Top Risks & Issues | Copy the top few from the RAID Log, with actions and owners. |
| 5 | 6 · Decisions Needed | Write each decision, who must make it, and by when. |
| 6 | 1 · Headline | Last: write one sentence, a confidence rating 1–5, and the trend since last time. |

# Making each section strong

Quality checks for each part of the report.

## 1 · Headline

- One honest sentence

- Confidence and trend are clear

## 2 · Outcomes

- Outcomes, not task lists

- Start, now and target shown

## 3 · Forecast

- A range, not a date

- What moved it

## 4 · Delivered & Learned

- Working and in use

- Learning is shared

## 5 · Top Risks & Issues

- Each has an action and owner

- Matches the RAID Log

## 6 · Decisions Needed

- Specific asks

- A named person and a date

# Facilitation tips

Write the headline last. Once the rest is done, the one-sentence summary is easy and honest.

Confidence beats colours. A 1–5 confidence rating with a trend says more than red, amber or green.

Lead with outcomes. Readers care about what changed for customers and the business, not tasks completed.

Always ask for something. If no decisions are needed, say so. Usually there's at least one.

Reuse the boards. Copy from the Release Forecast and RAID Log rather than writing from scratch.

Same shape every time. A consistent format lets readers spot changes quickly.

Common pitfalls: a wall of task updates; a single date instead of a range; hiding bad news until it's red; no decisions requested; different formats every time; writing it from scratch instead of from the boards.

# After the session

Straight away: Send it to the readers and walk the key ones through it in person or on a call.

Follow up: Chase the decisions needed before their dates.

Next report: Start by noting what changed since this one.

Over time: Ask readers what they use and what they don't, and trim the report.

# How it fits the toolkit

The project tools work together: run a Project Kickoff first, then build the Stakeholder Map, keep the RAID Log up to date, and refresh the Release Forecast after every iteration. Inside the project, teams use the lifecycle tools (Team Charter, Prioritisation, Sprint Planning and Review) and the break-down tools.

# Recreate it in your whiteboard

Paste this into your whiteboard's AI assistant (for example Miro AI or Atlassian Rovo) or a general assistant, to get an editable, native version of the board. Results vary by tool, so expect to tidy it up. For an exact copy, import the SVG as a locked background instead.

Create an editable whiteboard for “Outcome Status Report”, a workshop board.

Purpose: A one-page update built on outcomes, a forecast range, risks and the decisions needed, not traffic lights.

Layout: a wide landscape board (about 16:11). Make one frame per section below, placed as described. In each frame, add the section name as a heading, then its content as short text labels or empty fields to fill in. Leave space in each frame for sticky notes. Use the header colour given. Keep the wording as written and don't add extra content.

Header fields to fill in: Project, Report Date

Sections:

1. Headline: top full width, about 100% wide and 15% tall; header colour purple.

Subtitle: If they read only this

Content: Confidence: · Since last time: · In one sentence: · 1. 2 · 3. 4 · 5. ↑ · → · ↓ · Because:

2. Outcomes: middle left, about 65% wide and 40% tall; header colour emerald green.

Subtitle: What's changed for customers and the business

Content: Outcome: · Measure: · Start: · Now: · Target: · Trend:

3. Forecast: middle right, about 35% wide and 40% tall; header colour amber.

Subtitle: A range, with its assumptions

Content: Likely finish range: · Work done / remaining: · Scope change since last report: · Has the forecast moved? · No · Earlier · Later · Why: · See the Release Forecast board for the burn-up.

4. Delivered & Learned: bottom left, about 35% wide and 40% tall; header colour blue.

Subtitle: Since the last report

Content: Delivered (working, in use): · Learned (what changed our thinking):

5. Top Risks & Issues: bottom centre, about 35% wide and 40% tall; header colour red.

Subtitle: From the RAID log

Content: Risk / issue: · Action: · Owner:

6. Decisions Needed: bottom right, about 35% wide and 40% tall; header colour dark green.

Subtitle: What we need from you

Content: Decision: · From whom: · By when: · Next report:

Footer questions: “What has changed for our customers since the last report?” “What decision do we need, and from whom?”

Original board for reference: https://eparker71.github.io/better-delivery-toolkit/boards/status-report-board.html

Boards: https://eparker71.github.io/better-delivery-toolkit/boards/status-report-board.html  ·  Online guide: https://eparker71.github.io/better-delivery-toolkit/guides/facilitator-guide-status-report.html

© 2026 Eric Parker · CC BY 4.0 · eparker71.github.io/better-delivery-toolkit · Adapt it freely; please keep the credit and say what you changed.