# RAID Log Guide

How to keep a project's risks, assumptions, issues and dependencies visible, owned and acted on.

Facilitator Run-Sheet · Run a Project · Risks · Assumptions · Issues · Dependencies

“What's the risk we're not talking about?”

A RAID log brings four kinds of uncertainty into one view. Risks might happen; assumptions are believed but unproven; issues are happening now; dependencies are what you need from others, or they need from you. Keeping it on a board, reviewed every iteration, stops it becoming a spreadsheet nobody opens.

| Duration | Group | Use when | Output |
| --- | --- | --- | --- |
| 45 min to set up 15 min to review | PO, delivery lead, team reps | Any project with real uncertainty | Owned risks, tests & actions |

# Before the session

- Print the board at A3, or load the SVG as a digital background

- Bring the worries from the Project Kickoff and any existing risk register

- Bring the Dependency Map if you work with other teams

- Agree the scales: likelihood and impact as high / medium / low

# Agenda & run-sheet

| Time | Section | Facilitator notes |
| --- | --- | --- |
| 0–15 | R · Risks | List what might happen. Rate likelihood and impact. For the high ones, agree a response: avoid, reduce, transfer or accept. |
| 15–25 | A · Assumptions | What are we treating as true without evidence? Agree how and when to test the riskiest. |
| 25–35 | I · Issues | What's going wrong now? Agree the impact, an action, an owner and a due date. |
| 35–45 | D · Dependencies | What do we need from others, or they from us? Record who, by when, and the status. |
| Every iteration | Review (15 min) | Walk each quadrant: what's new, what's changed, what's closed? Move risks that happened to Issues. |

# Making each quadrant useful

Quality checks for each part of the log.

## R · Risks

- Written as cause → effect

- High risks have a response

- Each has an owner

## A · Assumptions

- Each has a test

- Proven or disproven ones are closed

## I · Issues

- An action and a due date

- Escalated when the team can't fix it

## D · Dependencies

- Named teams and dates

- Status kept current

- The other side knows

# Facilitation tips

Cause and effect. “If the supplier API is late, then integration testing slips” is actionable. “Supplier risk” isn't.

Test assumptions. An untested assumption is a risk in disguise. Use the 1% Experiment Canvas for the big ones.

Owners, not committees. Every row needs one named person who will act.

Keep it short. If the log has 80 rows, nobody reads it. Close, merge and prioritise.

Review in the open. A short review in the team's regular rhythm keeps it current and shared.

Escalate early. Issues the team can't solve go to the decision forum straight away.

ROAM for shared risks. In multi-team planning, SAFe sorts each risk as Resolved, Owned, Accepted or Mitigated. It's a quick way to make sure every risk ends with a decision.

Common pitfalls: vague risks with no cause or effect; no owners; never closing items; reviewing only at steering meetings; assumptions that are never tested; dependencies the other team doesn't know about.

# After the session

Straight away: Photograph the board or move it into your tool. Tell owners what they own.

Every iteration: Review in 15 minutes: new, changed, closed.

Monthly: Share the top risks and issues with the sponsor, with the actions being taken.

At the end: Review what happened. Which risks came true? What would you watch for next time?

# How it fits the toolkit

The project tools work together: run a Project Kickoff first, then build the Stakeholder Map, keep the RAID Log up to date, and refresh the Release Forecast after every iteration. Inside the project, teams use the lifecycle tools (Team Charter, Prioritisation, Sprint Planning and Review) and the break-down tools.

# Recreate it in your whiteboard

Paste this into your whiteboard's AI assistant (for example Miro AI or Atlassian Rovo) or a general assistant, to get an editable, native version of the board. Results vary by tool, so expect to tidy it up. For an exact copy, import the SVG as a locked background instead.

Create an editable whiteboard for “RAID Log”, a workshop board.

Purpose: Keep the project's risks, assumptions, issues and dependencies visible, owned and reviewed.

Layout: a wide landscape board (about 16:11). Make one frame per section below, placed as described. In each frame, add the section name as a heading, then its content as short text labels or empty fields to fill in. Leave space in each frame for sticky notes. Use the header colour given. Keep the wording as written and don't add extra content.

Header fields to fill in: Project, Last Reviewed

Sections:

1. Risks: top left, about 50% wide and 50% tall; header colour red.

Subtitle: Might happen · response: avoid · reduce · transfer · accept

Content: Risk: · Likelihood: · Impact: · Response: · Owner:

2. Assumptions: top right, about 50% wide and 50% tall; header colour amber.

Subtitle: Believed true · not yet proven

Content: Assumption: · How we'll test it: · By when: · Owner:

3. Issues: bottom left, about 50% wide and 50% tall; header colour orange.

Subtitle: Happening now

Content: Issue: · Impact: · Action: · Owner: · Due:

4. Dependencies: bottom right, about 50% wide and 50% tall; header colour blue.

Subtitle: We need from others · others need from us

Content: Dependency: · From → to: · Needed by: · Status: · Owner:

Footer questions: “What's the risk we're not talking about?” “Which assumption, if wrong, would hurt us most?”

Original board for reference: https://eparker71.github.io/agile-ways-of-working/raid-log-board.html

Boards: https://eparker71.github.io/agile-ways-of-working/raid-log-board.html  ·  Online guide: https://eparker71.github.io/agile-ways-of-working/facilitator-guide-raid-log.html

© 2026 Eric Parker · CC BY 4.0 · eparker71.github.io/agile-ways-of-working · Adapt it freely; please keep the credit and say what you changed.