# Project Close-out Guide

How to finish a project well: check what was achieved, hand over cleanly, learn, tie up loose ends and say thank you.

Facilitator Run-Sheet · Run a Project · Close

“What would we tell the next team that runs a project like this?”

Projects often just stop: people move on, loose ends stay loose, and the lessons are forgotten. A close-out session makes the ending deliberate. It compares what was delivered with the original goal, lists the benefits still to come (most value usually arrives after the project ends) and who will check them, confirms a clean handover to whoever runs the result, captures what we learned for the next project, gives every loose end an owner, and makes time to thank people. In agile delivery much of this happens continuously, but a project or programme with a defined end still needs a proper finish.

| Duration | Group | Use when | Output |
| --- | --- | --- | --- |
| 60–90 min | Team, sponsor, support & key stakeholders | A project or major phase is ending | Handover, owners, lessons & thanks |

# Before the session

- Print the board at A3, or load the SVG as a digital background

- Bring the original goal and success measures, from the Project Kickoff board if you used it

- Gather the actual results for each measure

- Invite whoever will own the result after the project: support, operations or the business

- Ask people to think about what they'd keep and change, beforehand

# Agenda & run-sheet

| Time | Section | Facilitator notes |
| --- | --- | --- |
| 0–5 | Set the tone | This is about learning and finishing well, not judging. Thank people up front. |
| 5–20 | 1 · Did We Achieve It? | Goal, what was delivered, and each measure's target and actual. What does the gap tell us? |
| 20–30 | 2 · Benefits Still to Come | List benefits not yet realised, when to expect them, how to measure them and who owns them. |
| 30–45 | 3 · Handover | Walk the checklist with the new owners. Anything not done becomes a loose end. |
| 45–65 | 4 · What We Learned | Silent writing, then cluster: keep doing, do differently, surprises. Pick the top three. |
| 65–75 | 5 · Loose Ends | Every open item gets an owner and a date. |
| 75–85 | 6 · Thanks & Celebrate | Name the people and teams to thank, decide how to celebrate, and who to share lessons with. |

# What a good close-out covers

Finish the work, then finish the project.

## Achievement

- Goal vs. delivered

- Target vs. actual

## Benefits

- Most arrive later

- An owner checks them

## Handover

- Support ready

- Nothing without an owner

## Lessons

- Keep, change, surprises

- Shared, not archived

## Thanks

- Name people

- Celebrate the finish

# Facilitation tips

Learn, don't blame. Ask what the system made easy or hard, not who got it wrong.

Bring the next owners. Handover works best with the people who'll run the result in the room.

Benefits need an owner. If no one is named to check the benefits, no one will.

Make lessons travel. Share the top three lessons with teams starting similar work, not just in a document.

Celebrate properly. Marking the end well helps people move on, and makes the next project easier to staff.

Close the small things. Accounts, licences, budgets and contracts left open cost money and create risk.

Common pitfalls: skipping close-out because people have moved on; a lessons-learned document no one reads; no owner for benefits; handing over to people who weren't involved; blaming individuals; forgetting to say thank you.

# After the session

Within a week: Send the summary, loose ends and owners to everyone involved.

Within a month: Share the top lessons with teams starting similar work.

At each benefit date: The owner checks the measure and reports it to the sponsor.

Next project: Bring these lessons to its kickoff and pre-mortem.

# How it fits the toolkit

The project tools work together: run a Project Kickoff first, then build the Stakeholder Map, keep the RAID Log up to date, and refresh the Release Forecast after every iteration. Inside the project, teams use the lifecycle tools (Team Charter, Prioritisation, Sprint Planning and Review) and the break-down tools.

# Recreate it in your whiteboard

Paste this into your whiteboard's AI assistant (for example Miro AI or Atlassian Rovo) or a general assistant, to get an editable, native version of the board. Results vary by tool, so expect to tidy it up. For an exact copy, import the SVG as a locked background instead.

Create an editable whiteboard for “Project Close-out”, a workshop board.

Purpose: Finish well: check what was achieved, hand over cleanly, capture what you learned, tie up loose ends and say thank you.

Layout: a wide landscape board (about 16:11). Make one frame per section below, placed as described. In each frame, add the section name as a heading, then its content as short text labels or empty fields to fill in. Leave space in each frame for sticky notes. Use the header colour given. Keep the wording as written and don't add extra content.

Header fields to fill in: Project, Date

Sections:

1. Did We Achieve It?: top left, about 50% wide and 35% tall; header colour purple.

Subtitle: Against the original goal

Content: Original goal: · What we delivered: · Measure: · Target: · Actual: · What it tells us:

2. Benefits Still to Come: top right, about 50% wide and 35% tall; header colour emerald green.

Subtitle: Most value arrives after the project ends

Content: Benefit: · Expected by: · Measured how: · Owner:

3. Handover: middle left, about 35% wide and 35% tall; header colour blue.

Subtitle: Who owns it now?

Content: Support team trained and ready · Documentation and runbooks handed over · Open defects and backlog given an owner · Monitoring and alerts owned · Access, licences and accounts sorted · Contracts and suppliers closed · Budget closed and reported · Handed to:

4. What We Learned: middle right, about 65% wide and 35% tall; header colour amber.

Subtitle: For the next project, not for the archive

Content: Keep doing: · Do differently: · Surprises: · What worked that we'd repeat? · What would we change? · What did we not see coming?

5. Loose Ends: bottom left, about 50% wide and 30% tall; header colour red.

Subtitle: Nothing left without an owner

Content: Item: · Owner: · By when:

6. Thanks & Celebrate: bottom right, about 50% wide and 30% tall; header colour dark green.

Content: People and teams to thank: · How we'll celebrate: · Share the story and lessons with:

Footer questions: “What would we tell the next team that runs a project like this?” “Who will check the benefits arrived, and when?”

Original board for reference: https://eparker71.github.io/agile-ways-of-working/project-closeout-board.html

Boards: https://eparker71.github.io/agile-ways-of-working/project-closeout-board.html  ·  Online guide: https://eparker71.github.io/agile-ways-of-working/facilitator-guide-project-closeout.html

© 2026 Eric Parker · CC BY 4.0 · eparker71.github.io/agile-ways-of-working · Adapt it freely; please keep the credit and say what you changed.