# Ageing WIP & SLE Guide

How to work out a service level expectation from cycle times, and use work item age to act before items are late.

Facilitator Run-Sheet · Manage Flow · Work Item Age · Percentiles · Service Level Expectation

“Which item is oldest, and what would it take to finish it today?”

Cycle time tells you how long finished work took; work item age tells you how long open work has been running. Plotting each open item's age against the team's cycle time percentiles shows which items are at risk while there's still time to act. The 85th percentile gives a service level expectation (SLE): “85% of our items finish within N days”. It's a forecast for a single item, not a target. Work item age and SLE are described in the Kanban Guide and in Daniel Vacanti's work on flow metrics.

| Duration | Group | Use when | Output |
| --- | --- | --- | --- |
| 45 min to set up 5 min each day | The team, with a flow-minded lead | Items surprise you by running late | An SLE & daily age checks |

# Before the session

- Print the board at A3, or load the SVG as a digital background

- Export start and finish dates for at least the last 20–30 finished items

- Agree when the clock starts (e.g. first in-progress column) and stops (e.g. Done)

- Know the in-progress columns of your board, left to right

- Small dot stickers or markers for plotting

# Agenda & run-sheet

| Time | Step | Facilitator notes |
| --- | --- | --- |
| 0–10 | 2 · Cycle Time Data | List recently finished items with start, finish and days (count partial days as a whole day). |
| 10–20 | Percentiles | Sort the days, smallest to largest. The 85th percentile is the value 85% of the way along the list. Repeat for 50th and 70th. |
| 20–25 | 3 · Our SLE | Write the 85th percentile into the SLE sentence, with the data range and the clock start and stop. |
| 25–35 | 1 · Ageing WIP Chart | Write the column names along the bottom and age in days up the side. Draw the three percentile lines. Plot each open item. |
| 35–45 | 4 · Act on Ageing Items | For each item past a line, agree the action. Swarm the ones past the 85th. |
| Daily | Update | Move dots up a day and across as items progress. Start the daily sync with the oldest items. |

# Reading the chart

What the dots tell you.

## Below the 50th

- On track

- No action needed

## Past the 50th

- Worth a mention

- Is anything slowing it?

## Past the 70th

- At risk

- Ask what's needed to finish

## Past the 85th

- Likely to miss the SLE

- Swarm it

## Dots high in early columns

- Stuck before real work started

- Check for blockers or big items

# Facilitation tips

Age is the leading signal. Cycle time is only known at the end. Age tells you about risk while you can still act.

An SLE isn't a target. Pushing people to hit it leads to gaming. Use it to spot risk and to answer “when?” for one item.

Use enough data. Twenty to thirty items gives a reasonable start. Recalculate monthly.

Start with the oldest. Walk the chart from the top. The oldest items need attention first.

Right-size before you start. Ask “can we finish this within our SLE?” when pulling work. If not, split it.

Link it to swarming. Use the 85th percentile as the age trigger in Buffering & Swarming.

Common pitfalls: treating the SLE as a deadline; using averages instead of percentiles; too little data; never updating the dots; ignoring items in early columns; tracking age but never acting on it.

# After the session

Straight away: Put the SLE sentence on the team board and in the team's working agreements.

Every day: Update the chart and discuss the oldest items first at the daily sync.

Each retro: Look at items that passed the 85th line. Why? Feed causes into Blocker Clustering.

Monthly: Recalculate the percentiles with new data and update the SLE.

# How it fits the toolkit

The flow pack works as a set. Kanban Board Design makes the workflow visible and limits WIP. Ageing WIP & SLE shows which items are at risk and sets the swarm triggers used in Buffering & Swarming. Blocker Clustering finds why work gets stuck, and the Skills Matrix shows who can swarm. Bring the results to retrospectives and the Team Health Check.

# Recreate it in your whiteboard

Paste this into your whiteboard's AI assistant (for example Miro AI or Atlassian Rovo) or a general assistant, to get an editable, native version of the board. Results vary by tool, so expect to tidy it up. For an exact copy, import the SVG as a locked background instead.

Create an editable whiteboard for “Ageing WIP & Service Level Expectation”, a workshop board.

Purpose: See how old each open item is compared with how long work usually takes, and act before it's late.

Layout: a wide landscape board (about 16:11). Make one frame per section below, placed as described. In each frame, add the section name as a heading, then its content as short text labels or empty fields to fill in. Leave space in each frame for sticky notes. Use the header colour given. Keep the wording as written and don't add extra content.

Header fields to fill in: Team, Date

Sections:

1. Ageing WIP Chart: top left, about 65% wide and 65% tall; header colour blue.

Subtitle: One dot per open item, in its current column

Content: COLUMN NAMES ↑ · IN-PROGRESS COLUMNS ONLY, LEFT TO RIGHT · 50th percentile · 70th · 85th = SLE · Draw each percentile as a line across the chart

2. Cycle Time Data: top right, about 35% wide and 65% tall; header colour emerald green.

Subtitle: Recently finished items

Content: Item: · Started: · Finished: · Days: · 50th percentile (days): · 70th percentile (days): · 85th percentile (days):

3. Our Service Level Expectation: bottom left, about 50% wide and 35% tall; header colour purple.

Subtitle: A forecast for one item, not a target

Content: 85% of our items finish within · days. · Based on how many items, from when to when: · The clock starts when: · The clock stops when:

4. Act on Ageing Items: bottom right, about 50% wide and 35% tall; header colour red.

Subtitle: Look at the oldest items first, every day

Content: Past the 50th · Mention it at the daily sync · Past the 70th · Ask what's needed to finish it · Past the 85th · Swarm it (see Buffering & Swarming) · Items to act on today:

Footer questions: “Which item is oldest, and what would it take to finish it today?” “How long does work usually take here, really?”

Original board for reference: https://eparker71.github.io/agile-ways-of-working/ageing-wip-board.html

Boards: https://eparker71.github.io/agile-ways-of-working/ageing-wip-board.html  ·  Online guide: https://eparker71.github.io/agile-ways-of-working/facilitator-guide-ageing-wip.html

© 2026 Eric Parker · CC BY 4.0 · eparker71.github.io/agile-ways-of-working · Adapt it freely; please keep the credit and say what you changed.