# Dependency Map Guide

How to make cross-team dependencies visible, track them, and find ways to remove them.

Facilitator Run-Sheet · Coordinate Teams · Dependency Board · Red String

“Which dependency could we remove instead of managing?”

Dependencies are one of the main reasons multi-team work runs late. The dependency board shows each team's work by iteration, with a red string linking each item to the team it depends on. Strings that run backwards in time, or that cross many teams, are the danger signs. The register tracks status and owners, and the reduce panel prompts the group to remove dependencies, not just manage them.

| Duration | Group | Use when | Output |
| --- | --- | --- | --- |
| 45–60 min, or as part of planning | A rep from each team, POs, delivery leads | Cross-team planning, then every sync | Visible, owned dependencies |

# Before the session

- Print the board at A1 or larger, or use a digital board with connectors

- Each team brings its planned items for the period

- Yellow, blue and pink stickies, red string or wool and tape (or digital connectors)

- Write the team names and iteration dates on the board in advance

# Agenda & run-sheet

| Time | Step | Facilitator notes |
| --- | --- | --- |
| 0–15 | Place work | Each team places its key items (yellow) in its row, in the iteration it plans to finish them. |
| 15–30 | Add dependencies | For each item that needs another team, add a blue sticky in the providing team's row, in the iteration it's needed. Link with red string. |
| 30–40 | Spot problems | Look for strings that point backwards in time, cross many teams, or land in a full iteration. Mark them pink. |
| 40–50 | 2 · Register | Record each dependency: who needs it, who provides it, what, by when, status and owner. |
| 50–60 | 3 · Reduce | For the riskiest dependencies, work through the reduce checklist. Agree the top one to remove. |

# Reading the board

Patterns that tell you where the risk is.

## Backwards strings

- Needed before it's planned

- Re-plan one side now

## Many strings to one team

- That team is a bottleneck

- Consider moving skills or people

## Long strings

- Big gaps in time add risk

- Can the need move later?

## 2 · Register

- Both teams agree each row

- Status is current

## 3 · Reduce

- Removal beats management

- Recurring links = team design issue

# Facilitation tips

Both sides agree. A dependency isn't real until the providing team has agreed to it and planned it.

Remove before you manage. Ask whether the needing team could do it themselves, with help or access.

Use contracts and stubs. Agreeing an interface early lets both teams work in parallel.

Watch the bottleneck team. If one team has most of the strings, fix the structure, not the schedule.

Keep it visible. Leave the board up for the period and update it at each Cross-Team Sync.

Learn from patterns. Recurring dependencies are a signal to change team boundaries or skills.

Common pitfalls: dependencies one side doesn't know about; only managing, never removing; ignoring backwards strings; a register nobody updates; blaming the providing team instead of fixing the system.

# After the session

Straight away: Photograph the board and update the register in your tools.

Every sync: Review status: agreed, at risk, blocked or done. Act on blocked ones that day.

Next planning: Bring patterns from this period. Which dependencies keep recurring?

Structure: If the same teams depend on each other every period, propose a team design change.

# How it fits the toolkit

The program tools coordinate several teams: agree Objectives & Key Results, plan together with the Cross-Team Planning board, make links visible on the Dependency Map, and keep in step with a regular Cross-Team Sync. Each team still plans, reviews and improves with the team-level tools.

# Recreate it in your whiteboard

Paste this into your whiteboard's AI assistant (for example Miro AI or Atlassian Rovo) or a general assistant, to get an editable, native version of the board. Results vary by tool, so expect to tidy it up. For an exact copy, import the SVG as a locked background instead.

Create an editable whiteboard for “Dependency Map”, a workshop board.

Purpose: Make cross-team dependencies visible: who needs what from whom, by when, and which ones are at risk.

Layout: a wide landscape board (about 16:11). Make one frame per section below, placed as described. In each frame, add the section name as a heading, then its content as short text labels or empty fields to fill in. Leave space in each frame for sticky notes. Use the header colour given. Keep the wording as written and don't add extra content.

Key: Yellow = Work item · Blue = Dependency · Pink = At risk · Red string = link

Sections:

1. Dependency Board: top full width, about 100% wide and 65% tall; header colour blue.

Subtitle: Place the item where it's needed · link it to who provides it

Content: Iteration 1: · Iteration 2: · Iteration 3: · Iteration 4: · Iteration 5: · Later: · Team 1 · Team 2 · Team 3 · Team 4 · Team 5 · Team 6

2. Dependency Register: bottom left, about 65% wide and 35% tall; header colour purple.

Subtitle: One row per dependency

Content: # · Needed by: · Provided by: · What: · By when: · Status: · Owner: · Status: agreed · at risk · blocked · done

3. Reduce Dependencies: bottom right, about 35% wide and 35% tall; header colour dark green.

Subtitle: Best dependency = no dependency

Content: Could the team do it themselves (skills, access)? · Could we re-order the work so it's needed later? · Could a stub, mock or contract unblock us? · Does it keep happening? Change team boundaries · Top dependency to remove: · Owner:

Footer questions: “Who are we waiting on, and do they know?” “Which dependency could we remove instead of managing?”

Original board for reference: https://eparker71.github.io/agile-ways-of-working/dependency-map-board.html

Boards: https://eparker71.github.io/agile-ways-of-working/dependency-map-board.html  ·  Online guide: https://eparker71.github.io/agile-ways-of-working/facilitator-guide-dependency-map.html

© 2026 Eric Parker · CC BY 4.0 · eparker71.github.io/agile-ways-of-working · Adapt it freely; please keep the credit and say what you changed.