# Sprint Planning Guide

How to agree a sprint goal, size the work to real capacity, and leave with a plan the team believes in.

Facilitator Run-Sheet · Build in Iterations · Sprint Goal · Capacity · Confidence Vote

“If we only achieve one thing this sprint, what should it be?”

Planning that is just dragging tickets into a sprint produces a list, not a plan. The board puts the sprint goal first, checks the work against real capacity, splits items into those needed for the goal and those that are also planned, and ends with a confidence vote so concerns surface before the sprint starts, not halfway through. It works for any iteration length. Scrum calls this event Sprint Planning.

| Duration | Group | Use when | Output |
| --- | --- | --- | --- |
| 1–2 h for a 2-week sprint | The whole team, PO included | The start of every iteration | A goal, a forecast & a first-day plan |

# Before the session

- Print the board at A3, or load the SVG as a digital background

- Make sure the top of the backlog is refined and ordered (Example Mapping helps)

- Know who is away, and the team's throughput or velocity for the last three sprints

- Bring the last Sprint Review's feedback and the last retro's actions

- Yellow and pink stickies, markers, and the team's Definition of Done

# Agenda & run-sheet

| Time | Section | Facilitator notes |
| --- | --- | --- |
| 0–10 | Context | The PO shares the product goal, recent feedback, and what's at the top of the backlog. Check the inputs. |
| 10–25 | 1 · Sprint Goal | Draft a goal that explains why the sprint is valuable. Agree how you'll know it's achieved. |
| 25–35 | 2 · Capacity | Count working days, absences and other commitments. Compare with recent throughput. |
| 35–65 | 4 · Selected Items | Pull items in priority order into “Needed for the goal”, then “Also planned”. Stop at capacity. |
| 65–80 | 5 · Risks & Dependencies | What could stop the goal? Who outside the team is needed, and when? Agree actions. |
| 80–90 | 6 · How We'll Start | Agree what starts on day one, who pairs or swarms, and the first thing to finish. |
| 90–95 | 7 · Confidence Vote | Fist of five. Anyone at 1 or 2 explains why; adjust the plan and re-vote. |

# Making each section strong

Quality checks for each part of the board.

## 1 · Sprint Goal

- One objective, not a list of items

- Says why, not just what

- Linked to the product goal

## 2 · Capacity

- Absences are counted

- Based on recent throughput, not hope

## 3 · Inputs Checked

- Review feedback and retro actions included

- The top items are ready

## 4 · Selected Items

- Goal items come first

- Room left for unplanned work

- Items are small

## 5 · Risks & Dependencies

- Each risk has an action

- External people know they're needed

## 6 · How We'll Start

- Focus on finishing, not starting everything

- Pairing or swarming planned

## 7 · Confidence Vote

- Low votes are explored, not overruled

- Re-vote after changes

# Facilitation tips

Goal first, items second. Agree why the sprint matters before choosing items. The goal guides trade-offs mid-sprint.

Plan to recent reality. Use the last three sprints' throughput. Planning to an ideal leads to carry-over and lost trust.

Leave slack. Plan to about 80% of capacity. Unplanned work always arrives.

It's a forecast. The team commits to the goal, not to every item. Say so out loud.

Plan the start. A clear first day stops everyone starting a different item at once.

Respect low votes. A 1 or a 2 is information. Ask what would raise it, and adjust the plan.

Common pitfalls: no sprint goal, or a goal that just lists items; ignoring absences; planning to 100% capacity; the PO assigning work to people; skipping the confidence vote; carrying over unfinished work without discussion.

# After the session

Straight away: Put the goal on the team board and update the backlog tool. Photograph the board.

Every day: At the daily sync, ask: are we on track for the sprint goal? What's blocking it?

Mid-sprint: If the goal is at risk, renegotiate scope with the PO early. Don't wait for the review.

End of sprint: Bring the goal to the Sprint Review and the retro: did we achieve it, and why?

# How it fits the toolkit

The lifecycle tools follow the work from start to finish: a Team Charter when a team forms, a Product Vision Board to agree why the product exists, the Prioritisation Board to decide what comes first, then Sprint Planning and Sprint Review each iteration, with a retrospective from the Retro Kit to close the loop. The break-down tools (Epic Canvas, Story Map, Story Splitting, Example Mapping) sit between vision and planning.

Boards: https://eparker71.github.io/agile-ways-of-working/sprint-planning-board.html  ·  Online guide: https://eparker71.github.io/agile-ways-of-working/facilitator-guide-sprint-planning.html

© 2026 Eric Parker · CC BY 4.0 · eparker71.github.io/agile-ways-of-working · Adapt it freely; please keep the credit and say what you changed.