# Cross-Team Planning Guide

How to plan a period of work across several teams, so shared objectives, dependencies and risks are agreed together.

Facilitator Run-Sheet · Coordinate Teams · Big-Room Planning · Shared Objectives

“What will we achieve together that no team could achieve alone?”

When several teams work on one product or outcome, planning in isolation creates surprises. Cross-team planning, often called big-room planning (SAFe calls it PI Planning), brings the teams together to agree shared objectives, build each team's plan for the coming iterations, place milestones, surface risks and needs, and agree a capacity split. It ends with a confidence vote, so the plan is one everyone believes in.

| Duration | Group | Use when | Output |
| --- | --- | --- | --- |
| Half a day to two days | All teams, POs, leaders, key experts | Every quarter or planning period | Objectives, team plans & known risks |

# Before the session

- Print the board at A1 or A0, or use a digital board. One board for the whole group

- Prepare the vision, the top priorities and the shared objectives in draft

- Each team brings its refined backlog and its capacity for each iteration

- Bring the Dependency Map and RAID Log, or plan to start them on the day

- Book a room or video setup where teams can work separately and come back together

- Agree the decision-maker for trade-offs between teams

# Agenda & run-sheet

| Time | Section | Facilitator notes |
| --- | --- | --- |
| 0–30 | Context | Leaders share the vision, the priorities and any fixed dates. Fill in 2 · Context & Constraints. |
| 30–60 | 1 · Shared Objectives | Present the draft objectives and their value. Teams ask questions; adjust if needed. |
| 60–180 | 3 · Team Plans (breakouts) | Each team plans its row: what will be done in each iteration, risks and needs. Place milestones. |
| 180–210 | Dependencies | Teams walk the board together and link dependencies on the Dependency Map. Resolve conflicts. |
| 210–240 | 5 · Risks · 6 · Capacity | Review risks to the plan and agree a response for each. Confirm the capacity split. |
| 240–255 | 4 · Confidence Vote | Fist of five for the whole plan. Explore low votes, adjust and re-vote. |

# Making each section strong

Quality checks for each part of the board.

## 1 · Shared Objectives

- Few, outcome-based

- Each has a business value

- Teams named against each

## 2 · Context & Constraints

- Fixed dates are real

- Capacity changes are known

## 3 · Team Plans

- Each team planned its own row

- Last iteration has slack

- Milestones placed

## 4 · Confidence Vote

- Every team votes

- Low votes change the plan

## 5 · Risks to the Plan

- Each has an owner and response

- Sort them ROAM: resolved, owned, accepted, mitigated

- Big ones go to the RAID Log

## 6 · Capacity Split

- Agreed before planning

- Includes a buffer for unplanned work

# Facilitation tips

Teams plan their own work. Leaders set objectives and priorities. Teams decide how much they can do.

Plan to capacity, not hope. Use each team's real throughput. Leave the last iteration lighter for catch-up and improvement.

Dependencies in the open. Walking the board together finds dependencies no single team saw.

Keep objectives few. More than 5–7 shared objectives usually means there's no real priority.

Decide trade-offs in the room. Have the decision-maker present, so conflicts are settled on the day.

Respect the vote. A low-confidence plan is a plan to fail. Re-plan until confidence is reasonable.

Common pitfalls: leaders dictating team plans; planning to 100% capacity; objectives that are feature lists; dependencies found after planning; no decision-maker present; ignoring a low confidence vote.

# After the session

Straight away: Photograph the board. Teams load their plans into their tools; publish the objectives.

Every week or two: Run the Cross-Team Sync to track progress, dependencies and impediments.

Mid-period: Check progress against the shared objectives; adjust plans if needed.

End of period: Hold a joint review and a cross-team retrospective before the next planning.

# How it fits the toolkit

The program tools coordinate several teams: agree Objectives & Key Results, plan together with the Cross-Team Planning board, make links visible on the Dependency Map, and keep in step with a regular Cross-Team Sync. Each team still plans, reviews and improves with the team-level tools.

# Recreate it in your whiteboard

Paste this into your whiteboard's AI assistant (for example Miro AI or Atlassian Rovo) or a general assistant, to get an editable, native version of the board. Results vary by tool, so expect to tidy it up. For an exact copy, import the SVG as a locked background instead.

Create an editable whiteboard for “Cross-Team Planning”, a workshop board.

Purpose: Plan a period of work across several teams: shared objectives, each team's plan, milestones and risks.

Layout: a wide landscape board (about 16:11). Make one frame per section below, placed as described. In each frame, add the section name as a heading, then its content as short text labels or empty fields to fill in. Leave space in each frame for sticky notes. Use the header colour given. Keep the wording as written and don't add extra content.

Header fields to fill in: Group, Planning Period

Sections:

1. Shared Objectives: top left, about 50% wide and 25% tall; header colour purple.

Subtitle: What we'll achieve together

Content: Objective: · Value (1–10): · Teams:

2. Context & Constraints: top right, about 50% wide and 25% tall; header colour slate grey.

Content: Product vision / goal: · Fixed dates & events: · Capacity changes (holidays, hiring): · Platform or architecture changes:

3. Team Plans: middle full width, about 100% wide and 55% tall; header colour blue.

Subtitle: One row per team · stickies in the iteration they'll be done

Content: Iteration 1: · Iteration 2: · Iteration 3: · Iteration 4: · Iteration 5: · Risks & needs: · Milestones · Team 1 · Team 2 · Team 3 · Team 4 · Team 5

4. Confidence Vote: bottom left, about 35% wide and 15% tall; header colour dark green.

Subtitle: Fist of five

Content: 1. 2 · 3. 4 · 5 · Anyone at 1–2? Explore, adjust the plan, re-vote.

5. Risks to the Plan: bottom centre, about 35% wide and 15% tall; header colour red.

6. Capacity Split: bottom right, about 35% wide and 15% tall; header colour sky blue.

Subtitle: Agree it up front

Content: Features %: · Tech debt & enablers %: · Unplanned buffer %:

Footer questions: “What will we achieve together that no team could achieve alone?” “Which dependency, if it slips, takes the plan with it?”

Original board for reference: https://eparker71.github.io/agile-ways-of-working/boards/cross-team-planning-board.html

Boards: https://eparker71.github.io/agile-ways-of-working/boards/cross-team-planning-board.html  ·  Online guide: https://eparker71.github.io/agile-ways-of-working/guides/facilitator-guide-cross-team-planning.html

© 2026 Eric Parker · CC BY 4.0 · eparker71.github.io/agile-ways-of-working · Adapt it freely; please keep the credit and say what you changed.