# Cross-Team Sync Guide

How to run a short, regular sync across teams that keeps shared objectives on track and clears blockers.

Facilitator Run-Sheet · Coordinate Teams · Scrum of Scrums · Cross-Team Impediments

“What's blocking another team that we could help with today?”

A cross-team sync, often called a Scrum of Scrums, is a short meeting where one person from each team shares progress toward the shared objectives, what's next, and what's blocking them. Its real job is to find and remove cross-team impediments: problems no single team can fix. Keep it short and focused on dependencies and blockers, not a status report.

| Duration | Group | Use when | Output |
| --- | --- | --- | --- |
| 15–30 min | One rep per team, a facilitator | Once or twice a week | Blockers owned, decisions made |

# Before the session

- Print the board at A3 or 11×17 and reuse it, or keep a digital copy

- Bring the Cross-Team Planning board and the Dependency Map

- Ask each team to choose its rep: whoever knows the current blockers best

- Yellow stickies and markers, and a visible timer

# Agenda & run-sheet

| Time | Step | Facilitator notes |
| --- | --- | --- |
| 0–12 | 1 · Team Updates | About 2 minutes per team: progress toward shared objectives, next up, blocked by or needs, dependencies at risk, confidence. |
| 12–20 | 2 · Impediments | Add new cross-team impediments. Move the ones being worked, and close resolved ones, saying what fixed them. |
| 20–27 | Problem-solve | Pick the top impediment. Agree who will act and when. Take longer discussions offline with the right people. |
| 27–30 | 3 · Decisions & Actions | Read back decisions and actions with owners and dates. |

# Making each part useful

What good looks like.

## 1 · Team Updates

- About progress toward objectives, not activity

- Blockers named clearly

- Confidence 1–5

## 2 · Cross-Team Impediments

- Each has an owner

- Resolved ones say what fixed it

## 3 · Decisions & Actions

- An owner and a due date

- Reviewed at the next sync

# Facilitation tips

Not a status meeting. If updates are lists of activity, steer back to objectives, dependencies and blockers.

Timebox hard. Keep to 15–30 minutes. Take deep discussions offline with the people who need to be there.

Right rep, not same rep. Send whoever knows the current blockers. It can change each time.

Look at the boards. Hold the sync in front of the Dependency Map so at-risk links are visible.

Escalate fast. Impediments the group can't solve go to leaders the same day.

Close the loop. Start each sync by checking last time's actions.

Common pitfalls: turning it into a status report for managers; running over time; the same blocker every week with no owner; solving problems in the meeting with the wrong people; no follow-up on actions.

# After the session

Straight away: Share the decisions and actions with all teams.

Within a day: Owners act on impediments, or escalate those they can't solve.

Next sync: Start by reviewing actions and impediments from last time.

Retro: Bring recurring impediments to a cross-team retrospective.

# How it fits the toolkit

The program tools coordinate several teams: agree Objectives & Key Results, plan together with the Cross-Team Planning board, make links visible on the Dependency Map, and keep in step with a regular Cross-Team Sync. Each team still plans, reviews and improves with the team-level tools.

# Recreate it in your whiteboard

Paste this into your whiteboard's AI assistant (for example Miro AI or Atlassian Rovo) or a general assistant, to get an editable, native version of the board. Results vary by tool, so expect to tidy it up. For an exact copy, import the SVG as a locked background instead.

Create an editable whiteboard for “Cross-Team Sync”, a workshop board.

Purpose: A short, regular check across teams: progress toward shared objectives, dependencies, and what's blocking whom.

Layout: a wide landscape board (about 16:11). Make one frame per section below, placed as described. In each frame, add the section name as a heading, then its content as short text labels or empty fields to fill in. Leave space in each frame for sticky notes. Use the header colour given. Keep the wording as written and don't add extra content.

Header fields to fill in: Group, Date

Sections:

1. Team Updates: top full width, about 100% wide and 50% tall; header colour blue.

Subtitle: One person per team · about 2 minutes each

Content: Team: · Progress toward shared objectives: · Next up: · Blocked by / needs: · Dependencies at risk: · Conf. 1–5:

2. Cross-Team Impediments: bottom left, about 65% wide and 50% tall; header colour orange.

Subtitle: Problems no single team can solve

Content: New · Being worked · Resolved · Raised today · Has an owner and a next step · Say what fixed it

3. Decisions & Actions: bottom right, about 35% wide and 50% tall; header colour dark green.

Content: Decision / action: · Owner: · Due:

Footer questions: “What's blocking another team that we could help with today?” “Are we still on track for the shared objectives?”

Original board for reference: https://eparker71.github.io/agile-ways-of-working/boards/cross-team-sync-board.html

Boards: https://eparker71.github.io/agile-ways-of-working/boards/cross-team-sync-board.html  ·  Online guide: https://eparker71.github.io/agile-ways-of-working/guides/facilitator-guide-cross-team-sync.html

© 2026 Eric Parker · CC BY 4.0 · eparker71.github.io/agile-ways-of-working · Adapt it freely; please keep the credit and say what you changed.