# Release Readiness & Strategy Guide

How to plan how a change reaches users, decide go or no-go, know how to undo it, and tell the people who need to know.

Facilitator Run-Sheet · Engineering Practices · Separate Deploy from Release

“If this goes wrong at the worst moment, what's our plan?”

Deploying puts new code into production; releasing makes it available to users. Keeping them separate is one of the most useful ideas in modern delivery: with feature flags, canary releases, blue-green switches or phased rollouts, a team can deploy safely and then release a little at a time, watching as it goes. The board walks through the release approach, a go/no-go checklist agreed in advance, a rollback plan, who needs to know, and the checks after release. It's useful for engineering teams and for project and programme managers coordinating a larger release.

| Duration | Group | Use when | Output |
| --- | --- | --- | --- |
| 45–60 min, a week or so before | Team, product owner, support & operations | Any release that's large, risky or visible | A release plan & a go/no-go decision |

# Before the session

- Print the board at A3 or 11×17, or load the SVG as a digital background

- List what's in the release and who it affects

- Check what your platform supports: feature flags, canary or blue-green deployment

- Invite support, operations and anyone who talks to customers

- Find out whether a formal change approval is needed, and its lead time

# Agenda & run-sheet

| Time | Section | Facilitator notes |
| --- | --- | --- |
| 0–10 | 1 · What's Releasing | Agree the version, the outcome for users, the main changes, who's affected, and the deploy and switch-on dates. |
| 10–20 | 2 · Release Approach | Choose how users will get it. Can we release a little at a time instead of all at once? |
| 20–30 | 3 · Go / No-Go Checklist | Agree the checklist now, so the go decision on the day is quick and calm. |
| 30–40 | 4 · Rollback & Recovery | How will we know it's gone wrong, and how will we undo it? What can't be undone? |
| 40–50 | 5 · Who Needs to Know | List each audience, what they need, when and how, and who tells them. |
| 50–55 | 6 · After Release | Set the date to check the outcome and to remove any feature flag. |
| Release day | Go / no-go | Run through the checklist, record the decision, and keep someone on hand afterwards. |

# Ways to release

Smaller and more gradual is usually safer.

## Feature flag

- Deploy switched off

- Turn on for some, then all

- Remove the flag later

## Canary

- A small share first

- Watch, then widen

## Blue-green

- Two copies of production

- Switch traffic back to undo

## Phased rollout

- By region or group

- Learn between phases

## Big bang

- Everyone at once

- Needs the strongest rollback

# Facilitation tips

Agree the checklist early. Deciding what “ready” means on release day leads to pressure and shortcuts.

Test the rollback. A rollback plan that's never been tried is a hope, not a plan.

Know what can't be undone. Data migrations, emails and payments often can't be rolled back; plan for them separately.

Release a little at a time. A canary or phased rollout turns one big risk into several small ones.

Remove old flags. Every flag left in place adds complexity; set a date to take it out.

Make releases boring. The goal is releases so small and frequent that they stop needing a meeting.

Common pitfalls: treating deploy and release as the same thing; writing the checklist on the day; an untested rollback; forgetting support or customer-facing teams; leaving feature flags in forever; releasing on a Friday evening with no one around.

# After the session

Release day: Watch the monitoring closely and keep the agreed person on hand.

Within a week: Check the outcome measure, and roll out further if it's going well.

By the agreed date: Remove the feature flag and any old code.

Next retro: Review what went well and what to change for the next release.

# How it fits the toolkit

The delivery engineering tools work as a set. SDLC at a Glance shows where each stage of the lifecycle fits. The Delivery Pipeline Canvas maps how changes reach production, the Test Strategy decides how quality is built in, and Release Readiness & Strategy plans each release. The Continuous Delivery Health Check tracks the practices over time, and Delivery Metrics & Tech Debt measures the results. For the wider flow from idea to customer, use the Value Stream Map.

# Recreate it in your whiteboard

Paste this into your whiteboard's AI assistant (for example Miro AI or Atlassian Rovo) or a general assistant, to get an editable, native version of the board. Results vary by tool, so expect to tidy it up. For an exact copy, import the SVG as a locked background instead.

Create an editable whiteboard for “Release Readiness & Strategy”, a workshop board.

Purpose: Plan how a change reaches users, check it's ready, know how to undo it, and tell the people who need to know.

Layout: a wide landscape board (about 16:11). Make one frame per section below, placed as described. In each frame, add the section name as a heading, then its content as short text labels or empty fields to fill in. Leave space in each frame for sticky notes. Use the header colour given. Keep the wording as written and don't add extra content.

Header fields to fill in: Release, Target Date

Sections:

1. What's Releasing: top left, about 35% wide and 35% tall; header colour purple.

Content: Release / version: · Outcome for users: · Main changes: · Who's affected: · Deploy date: · Switch-on date:

2. Release Approach: top right, about 65% wide and 35% tall; header colour blue.

Subtitle: Tick one or combine · deploying isn'T the same as releasing

Content: Big bang · Feature flag · Canary · Everyone gets it at once. · Deploy switched off, then turn it · A small share of users first, · Simple, but the riskiest. · on when ready, for some or all. · then more if all is well. · Blue-green · Phased rollout · Beta / early access · Switch traffic to a new copy; · By region, customer group · Volunteers try it first and · switch back if it goes wrong. · or channel, one at a time. · give feedback.

3. Go / No-Go Checklist: middle left, about 50% wide and 40% tall; header colour dark green.

Subtitle: Agree the list before the day

Content: Definition of Done met for every item · Pipeline green, no open critical defects · Performance and security checks done · Rollback tested, not just written down · Monitoring and alerts ready · Support and operations briefed · Release notes and messages ready · Data migration rehearsed (if any) · Change approval recorded (if needed) · Someone on hand after release · Decision: · Go · No-go · Decided by: · When:

4. Rollback & Recovery: middle right, about 50% wide and 40% tall; header colour red.

Subtitle: Plan to undo it before you do it

Content: If it goes wrong, we'll see: · We'll undo it by: · Time to undo: · Who decides to roll back: · What we can't undo (data, messages): · Rollback last tested on:

5. Who Needs to Know: bottom left, about 65% wide and 25% tall; header colour sky blue.

Subtitle: Users, support, sales, other teams

Content: Audience: · WHAT THEY NEED TO KNOW · When: · How: · Owner:

6. After Release: bottom right, about 35% wide and 25% tall; header colour amber.

Content: Check the outcome on: · Remove the feature flag by: · What we learned:

Footer questions: “If this goes wrong at the worst moment, what's our plan?” “Could we release this a little at a time?”

Original board for reference: https://eparker71.github.io/agile-ways-of-working/boards/release-readiness-board.html

Boards: https://eparker71.github.io/agile-ways-of-working/boards/release-readiness-board.html  ·  Online guide: https://eparker71.github.io/agile-ways-of-working/guides/facilitator-guide-release-readiness.html

© 2026 Eric Parker · CC BY 4.0 · eparker71.github.io/agile-ways-of-working · Adapt it freely; please keep the credit and say what you changed.