# Stakeholder Map Guide

How to identify the people who affect or are affected by the work, and plan how to involve each of them.

Facilitator Run-Sheet · Run a Project · Influence vs. Interest · Communication Plan

“Who could stop this, and what do they need from us?”

Agile work depends on fast feedback and clear decisions, and both depend on the right people being involved. The map places each stakeholder by influence and interest, which suggests how closely to involve them. The register records what each one wants and worries about, and the communication plan turns that into a regular rhythm. Watch-outs capture who might block the work and who is missing.

| Duration | Group | Use when | Output |
| --- | --- | --- | --- |
| 60–90 min | PO, delivery lead, sponsor, team reps | At kickoff, then every month or so | A map, a register & a comms plan |

# Before the session

- Print the board at A3 or 11×17 (Tabloid), or larger, or load the SVG as a digital background

- List known stakeholders in advance: sponsors, users, customers, other teams, suppliers, regulators

- Bring an org chart if the organisation is large or new to the team

- Yellow and pink stickies and markers

- Agree that the map may be sensitive, and decide who it will be shared with

# Agenda & run-sheet

| Time | Section | Facilitator notes |
| --- | --- | --- |
| 0–15 | Brainstorm | Write one stakeholder per yellow sticky: people and groups. Ask “who is affected?” as well as “who decides?” |
| 15–35 | 1 · Place them | Place each sticky on the grid by influence and interest. Compare them to each other and discuss disagreements. |
| 35–55 | 2 · Register | For the Manage Closely and Keep Satisfied groups first, write what they want, what worries them, and how you'll engage. |
| 55–75 | 3 · Communication Plan | Group stakeholders into audiences. Agree what each needs, the format, the frequency and the owner. |
| 75–85 | 4 · Watch-outs | Who could block this? Who is missing? Add pink stickies and agree actions. |
| 85–90 | Close | Agree who keeps the map up to date and when it's next reviewed. |

# What each quadrant means

Where a stakeholder sits suggests how to involve them, but always ask what they want too.

## Manage Closely

- Involve in key decisions

- Meet regularly

- Surprises here are costly

## Keep Satisfied

- Consult on what matters to them

- Short, focused updates

## Keep Informed

- Regular updates

- Invite to reviews

- Great source of feedback

## Monitor

- Light-touch updates

- Watch for changes in interest

## Register & Comms Plan

- Every Manage Closely stakeholder has an owner

- Formats match how people like to hear

# Facilitation tips

Think beyond the org chart. Users, support staff, other teams and suppliers are stakeholders too.

Influence isn't just rank. Some people have little authority but a lot of influence. Place them honestly.

Ask, don't assume. Check what stakeholders want by talking to them, not by guessing in the room.

Reviews are engagement. Invite Keep Informed and Manage Closely stakeholders to Sprint Reviews.

Move people. Interest and influence change. Re-map monthly or when something big shifts.

Handle with care. Notes about individuals can be sensitive. Agree where the board is kept.

Common pitfalls: only listing senior people; mapping once and never again; a comms plan that's just “monthly status report”; writing unkind notes about individuals; nobody owning the relationship with key stakeholders.

# After the session

Straight away: Store the board where the agreed audience can see it, and nowhere else.

This week: Owners contact their key stakeholders to check the register is right.

Every iteration: Use the communication plan; invite the right people to the Sprint Review.

Monthly: Review the map and move stakeholders as their interest or influence changes.

# How it fits the toolkit

The project tools work together: run a Project Kickoff first, then build the Stakeholder Map, keep the RAID Log up to date, and refresh the Release Forecast after every iteration. Inside the project, teams use the lifecycle tools (Team Charter, Prioritisation, Sprint Planning and Review) and the break-down tools.

# Recreate it in your whiteboard

Paste this into your whiteboard's AI assistant (for example Miro AI or Atlassian Rovo) or a general assistant, to get an editable, native version of the board. Results vary by tool, so expect to tidy it up. For an exact copy, import the SVG as a locked background instead.

Create an editable whiteboard for “Stakeholder Map”, a workshop board.

Purpose: See who affects or is affected by the work, how much they care, and how you'll keep each of them involved.

Layout: a wide landscape board (about 16:11). Make one frame per section below, placed as described. In each frame, add the section name as a heading, then its content as short text labels or empty fields to fill in. Leave space in each frame for sticky notes. Use the header colour given. Keep the wording as written and don't add extra content.

Key: Yellow Sticky = Stakeholder · Pink Sticky = Concern / Blocker

Sections:

1. Influence vs. Interest: top left, about 55% wide and 70% tall; header colour blue.

Subtitle: One sticky per person or group

Content: Keep Satisfied · Manage Closely · High influence · low interest · consult on what matters to them · High influence · high interest · involve in key decisions · Monitor · Keep Informed · Low influence · low interest · light-touch updates · Low influence · high interest · regular updates, invite feedback · Low interest: · Interest →: · High interest:

2. Stakeholder Register: top right, about 45% wide and 70% tall; header colour purple.

Subtitle: What they want and how we engage

Content: Stakeholder: · Wants / worries: · How & how often: · Owner:

3. Communication Plan: bottom left, about 65% wide and 30% tall; header colour sky blue.

Subtitle: Right message · right people · right rhythm

Content: Audience: · What they need: · Format: · Frequency: · Owner:

4. Watch-outs: bottom right, about 35% wide and 30% tall; header colour red.

Content: Who could block this, and why? · Who is missing from the map?

Footer questions: “Who will be affected by this, and have we asked them?” “Who could stop this, and what do they need from us?”

Original board for reference: https://eparker71.github.io/agile-ways-of-working/boards/stakeholder-map-board.html

Boards: https://eparker71.github.io/agile-ways-of-working/boards/stakeholder-map-board.html  ·  Online guide: https://eparker71.github.io/agile-ways-of-working/guides/facilitator-guide-stakeholder-map.html

© 2026 Eric Parker · CC BY 4.0 · eparker71.github.io/agile-ways-of-working · Adapt it freely; please keep the credit and say what you changed.